## BrMaint Plan
[11 empty] | *Based on Gov. As-Passed Budget | [12 empty] | *Based on 12-16-20 Final Review Version and Level Maintenance Funding
[11 empty] | Interstate Bridge - Large Culvert |  |  |  | 2250000 | 2025000 | 225000 | [6 empty] | Interstate Bridge - Large Culvert |  |  |  | 50000 | 45000 | 5000
[11 empty] | Interstate Bridge Maintenance (TBI and projects) |  |  |  | 1985000 | 1786500 | 198500 | [6 empty] | Interstate Bridge Maintenance |  |  |  | 1566250 | 1409625 | 156625
[11 empty] | State Bridge - Large Culvert |  |  |  | 125000 | 100000 | 25000 | [6 empty] | State Bridge - Large Culvert |  |  |  | 125000 | 100000 | 25000
[11 empty] | State Bridge - Emergent Needs |  |  |  | 1050000 | 840000 | 210000 | [6 empty] | State Bridge Emergent Needs |  |  |  | 1050000 | 840000 | 210000
[11 empty] | State Bridge Maintenance (TBI and Projects) |  |  |  | 1895000 | 1516000 | 379000 | [6 empty] | State Bridge Maintenance |  |  |  | 2315000 | 1852000 | 463000
[11 empty] | Bennington BM20101 *BS FOB Project |  |  |  | 105000 | 0 | 105000
[11 empty] | Essex BM19501 *BS FOB Project |  |  |  | 500000 | 400000 | 100000
[11 empty] | Fair Haven BM19301 *BS FOB Project |  |  |  | 200000 | 160000 | 40000
[11 empty] | Newport BM19902 *BS FOB Project |  |  |  | 500000 | 400000 | 100000
[11 empty] | Springfield BM19201 *BS FOB Project |  |  |  | 200000 | 160000 | 40000
[6 empty] | * These number match those presented to the Transportation Committees and represent a plan; however $1,546,000 is allocated to the districts to be spent as needed to meet their goals /performance measures and, as such, has been removed from available funding in this plan |  |  |  |  | Maintaining Structures |  |  |  | 1789278 | 0 | 1789278 | [6 empty] | Maintaining Structures |  |  |  | 1789278 | 0 | 1789278
[11 empty] | Maintaining Bridges |  |  |  | 800000 | 0 | 800000 | [6 empty] | Maintaining Bridges |  |  |  | 800000 | 0 | 800000
[11 empty] | Washing Bridges |  |  |  | 440000 | 0 | 440000 | [6 empty] | Washing Bridges |  |  |  | 440000 | 0 | 440000
[11 empty] | Applying Preservation Materials |  |  |  | 620000 | 0 | 620000 | [6 empty] | Applying Preservation Materials |  |  |  | 620000 | 0 | 620000
[11 empty] | * Unavailable Allocation to Districts /Regions |  |  |  | -1546000 | 0 | -1546000 | [6 empty] | * Unavailable Allocation to Districts /Regions |  |  |  | -1546000 | 0 | -1546000
*this assumed level funded into FY '22
[18 empty] | Maintenance Appropriation Total |  |  | PDB Bridge Appropriation Total | [9 empty] | Maintenance Appropriation Total |  |  | PDB Bridge Appropriation Total
[11 empty] | TOTALS |  |  |  | 10913278 | 7387500 | 3525778 | 2103278 | 0 | 2103278 | 8810000 | 7387500 | 1422500 | TOTALS |  |  |  | 7209528 | 4246625 | 2962903 | 2103278 | 0 | 2103278 | 5106250 | 4246625 | 859625
2020 and 2021 Maintenance Plan | [11 empty] | FY'21 Expected Expenditure |  |  | FY '21 Running Balance |  |  | FY '21 MAB Projects |  |  | FY '21 PDB Projects |  |  |  | FY '22 Expected Expenditure |  |  | FY '22 Running Balance |  |  | FY '22 MAB Running Balance |  |  | FY '22 PDB Running Balance
Action | Delivering | Appropriation | Structures to Scope | Status | Comments | Town | Project Number | Route | Bridge # | Finding Date | Description of Work | Total | Federal | State | Total | Federal | State | Total | Federal | State | Total | Federal | State | Appropriation | Total | Federal | State | Total | Federal | State | Total | Federal | State | Total | Federal | State
Sven | Maintenance HQ | Interstate Bridge |  | FY22 in Vpins, advertise in spring. | Permitting should be completed by 3/19/21, has instream work so wouldnt be able to start until July 1 | Barton | BM20903 | I-91 | 105-1 |  | bridge maintenance | 5000 | 4500 | 500 | 10908278 | 7383000 | 3525278 | 0 | 0 | 0 | 5000 | 4500 | 500 | Interstate Bridge | 100000 | 90000 | 10000 | 7109528 | 4156625 | 2952903 | 0 | 0 | 0 | 100000 | 90000 | 10000
Kristin | Structures | State Bridge |  |  |  | Bennington | BM20101 | VT-279 | 11 |  | evaluation and strengthening | 25000 | 0 | 25000 | 10883278 | 7383000 | 3500278 | 0 | 0 | 0 | 25000 | 0 | 25000 | State Bridge | 28188 | 0 | 28188 | 7081340 | 4156625 | 2924715 | 0 | 0 | 0 | 28188 | 0 | 28188
Sven | Maintenance HQ | State Bridge |  | Completed | No reporting format in VPINS for tracking; No action required; programmed; substantial completion 7/17/2019 | Berlin | BM19703 | VT 12 | 68 |  | Repair Hole in Backwall | 0 | 0 | 0 | 10883278 | 7383000 | 3500278 | 0 | 0 | 0 | 0 | 0 | 0 | State Bridge | 0 | 0 | 0 | 7081340 | 4156625 | 2924715 | 0 | 0 | 0 | 0 | 0 | 0
Sven | Maintenance HQ | State Bridge |  | FY22 in Vpins, advertise in spring. | Need to develop plans, permitting | Berlin | BM20701 | VT-12 | 64 |  | bridge maintenance | 5000 | 4000 | 1000 | 10878278 | 7379000 | 3499278 | 0 | 0 | 0 | 5000 | 4000 | 1000 | State Bridge | 100000 | 80000 | 20000 | 6981340 | 4076625 | 2904715 | 0 | 0 | 0 | 100000 | 80000 | 20000
Sven | Maintenance HQ | State Bridge |  | Ready to Advertise | will be advertising before the first of the year | Bloomfield | BM20902 | VT-102 | 9 |  | bridge maintenance | 130000 | 104000 | 26000 | 10748278 | 7275000 | 3473278 | 0 | 0 | 0 | 130000 | 104000 | 26000 | State Bridge | 0 | 0 | 0 | 6981340 | 4076625 | 2904715 | 0 | 0 | 0 | 0 | 0 | 0
Sven | Maintenance HQ | State Bridge |  | Completed | Substantial completion 8/7/2019 | Braintree | BM19402 | VT 12 | 46 |  | Install kneewall and address scour | 0 | 0 | 0 | 10748278 | 7275000 | 3473278 | 0 | 0 | 0 | 0 | 0 | 0 | State Bridge | 0 | 0 | 0 | 6981340 | 4076625 | 2904715 | 0 | 0 | 0 | 0 | 0 | 0
| Structures | n/a | Continue to monitor |  | i believe this project has been programmed? | Brattleboro |  | I-91 | 4 |  | Install fascia catch | 0 | 0 | 0 | 10748278 | 7275000 | 3473278 | 0 | 0 | 0 | 0 | 0 | 0 | n/a | 0 | 0 | 0 | 6981340 | 4076625 | 2904715 | 0 | 0 | 0 | 0 | 0 | 0
Sven | Maintenance HQ | Interstate Bridge |  | Completed | No action required; programmed | Brattleboro | BM19203 | I-91 / VT 9 | 7 / 54A |  | Mill and Fill with Concrete Repair | 762503 | 686252.7 | 76250.3 | 9985775 | 6588747.3 | 3397027.7 | 0 | 0 | 0 | 762503 | 686252.7 | 76250.3 | Interstate Bridge | 0 | 0 | 0 | 6981340 | 4076625 | 2904715 | 0 | 0 | 0 | 0 | 0 | 0
|  | n/a | Low Priority - Town Responsibility |  | No action required; TH over US-4 (low priority) | Castelton |  | US 4 | 9 E&W |  | Replace Approach Rail | 0 | 0 | 0 | 9985775 | 6588747.3 | 3397027.7 | 0 | 0 | 0 | 0 | 0 | 0 | n/a | 0 | 0 | 0 | 6981340 | 4076625 | 2904715 | 0 | 0 | 0 | 0 | 0 | 0
Sven | Maintenance HQ | State Bridge |  | FY22 in Vpins, ready to advertise |  | Clarendon | BM20302 | US-7 | 90 N/S |  | bridge maintenance | 105000 | 84000 | 21000 | 9880775 | 6504747.3 | 3376027.7 | 0 | 0 | 0 | 105000 | 84000 | 21000 | State Bridge | 0 | 0 | 0 | 6981340 | 4076625 | 2904715 | 0 | 0 | 0 | 0 | 0 | 0
Sven | Maintenance HQ | Interstate Bridge |  | Ready to Advertise | FHWA will approve construction funding if resubmitted | Derby | BM20905 | VT-191 | 1 |  | shoring the backwalls, limited concrete repair, bituminous concrete deck overlay and pavement markings | 530000 | 477000 | 53000 | 9350775 | 6027747.3 | 3323027.7 | 0 | 0 | 0 | 530000 | 477000 | 53000 | Interstate Bridge | 0 | 0 | 0 | 6981340 | 4076625 | 2904715 | 0 | 0 | 0 | 0 | 0 | 0
Kristin | Structures | Interstate Bridge |  | Completed |  | District 5 | BM20502 | I-89 | 29 and 79 |  | strategic repair of US-2 bridges over I-89 | 732191 | 658971.9 | 73219.1 | 8618584 | 5368775.4 | 3249808.6 | 0 | 0 | 0 | 732191 | 658971.9 | 73219.1 | Interstate Bridge | 0 | 0 | 0 | 6981340 | 4076625 | 2904715 | 0 | 0 | 0 | 0 | 0 | 0
Sven | Maintenance HQ | State Bridge |  | FY22 in Vpins, advertise in spring. | Waiting on NEPA Re-Eval. Has instream work, cant start until after July 1. FY'20 FOB Project Cost and not under Maintenance; No action required; programmed | Essex | BM19501 | VT 128 | 1 |  | Line existing culvert | 12577 | 10061.6 | 2515.4 | 8606007 | 5358713.8 | 3247293.2 | 0 | 0 | 0 | 12577 | 10061.6 | 2515.4 | State Bridge | 500000 | 400000 | 100000 | 6481340 | 3676625 | 2804715 | 0 | 0 | 0 | 500000 | 400000 | 100000
Sven | Maintenance HQ | State Bridge | Plans Complete. Coordinate w/ Paving. | Completed | No action required; programmed | Fair Haven | BM19301 | US 4 | 3 E&W |  | Concrete Repairs | 230144 | 184115.2 | 46028.8 | 8375863 | 5174598.6 | 3201264.4 | 0 | 0 | 0 | 230144 | 184115.2 | 46028.8 | State Bridge | 0 | 0 | 0 | 6481340 | 3676625 | 2804715 | 0 | 0 | 0 | 0 | 0 | 0
|  | n/a | Low Priority - Town Responsibility |  | No action required; TH over US-4 (low priority) | Fair Haven |  | US 4 | 4 E&W |  | Replace Approach Rail | 0 | 0 | 0 | 8375863 | 5174598.6 | 3201264.4 | 0 | 0 | 0 | 0 | 0 | 0 | n/a | 0 | 0 | 0 | 6481340 | 3676625 | 2804715 | 0 | 0 | 0 | 0 | 0 | 0
|  | n/a |  |  | Kevin/Pam to discuss status | Fair Haven - Rutland Town |  | US 4 | Numerous |  | Joints, compression seal, downspouts | 0 | 0 | 0 | 8375863 | 5174598.6 | 3201264.4 | 0 | 0 | 0 | 0 | 0 | 0 | n/a | 0 | 0 | 0 | 6481340 | 3676625 | 2804715 | 0 | 0 | 0 | 0 | 0 | 0
Sven | Maintenance HQ | State Bridge |  | Completed |  | Fayston | BM20506 | VT-17 | 37 |  | bridge maintenance | 223845 | 179076 | 44769 | 8152018 | 4995522.6 | 3156495.4 | 0 | 0 | 0 | 223845 | 179076 | 44769 | State Bridge | 0 | 0 | 0 | 6481340 | 3676625 | 2804715 | 0 | 0 | 0 | 0 | 0 | 0
Sven | Maintenance HQ | Interstate Bridge | To be programmed. | Completed | Program as BM20801 - 90%-10% funded project | Georgia | BM20801 | US 7 / I-89 | 163A / 90 |  | Joint/drainage system | 45000 | 40500 | 4500 | 8107018 | 4955022.6 | 3151995.4 | 0 | 0 | 0 | 45000 | 40500 | 4500 | Interstate Bridge | 0 | 0 | 0 | 6481340 | 3676625 | 2804715 | 0 | 0 | 0 | 0 | 0 | 0
Sven | Maintenance HQ | State Bridge |  | Ready to Advertise - On Hold | Spring 2021 Advertise | Glover | BM20901 | VT-16 | 19 |  | bridge maintenance | 180000 | 144000 | 36000 | 7927018 | 4811022.6 | 3115995.4 | 0 | 0 | 0 | 180000 | 144000 | 36000 | State Bridge | 0 | 0 | 0 | 6481340 | 3676625 | 2804715 | 0 | 0 | 0 | 0 | 0 | 0
Sven | Maintenance HQ | State Bridge |  | FY22 in Vpins, advertise in spring. | Need to develop plans, permitting | Granville | BM20407 | VT-100 | 159 |  | bridge maintenance | 5000 | 4000 | 1000 | 7922018 | 4807022.6 | 3114995.4 | 0 | 0 | 0 | 5000 | 4000 | 1000 | State Bridge | 100000 | 80000 | 20000 | 6381340 | 3596625 | 2784715 | 0 | 0 | 0 | 100000 | 80000 | 20000
Sven | Maintenance HQ | Maintenance | Per Sven, work completed and paid | Completed | Project did not get completed to hit '19 and funded by '20; 2018 BIF for bridge 41C and 41N | Hartford | MVT-073 | I-91 | 41C and 41N | 2018-06-28 | Backwall /deck repair | 0 | 0 | 0 | 7922018 | 4807022.6 | 3114995.4 | 0 | 0 | 0 | 0 | 0 | 0 | Maintenance | 0 | 0 | 0 | 6381340 | 3596625 | 2784715 | 0 | 0 | 0 | 0 | 0 | 0
Sven | Maintenance - HQ | Interstate Bridge | Awarded to ECI | Completed | Temporary fixes. MaintHQ estimate - $25,000 / Bid estimate - $30,000; completion 10/30/2019 | Hartford | BM19401 | I-91 | 44 N&S |  | Joints, bracing | 0 | 0 | 0 | 7922018 | 4807022.6 | 3114995.4 | 0 | 0 | 0 | 0 | 0 | 0 | Interstate Bridge | 0 | 0 | 0 | 6381340 | 3596625 | 2784715 | 0 | 0 | 0 | 0 | 0 | 0
Kristin | Structures | Interstate Bridge |  |  |  | Hartford | BM20405 | I-91 | 46 |  | Replacement of existing bridge and approach rail and reinstallation of chain link fencing | 339210 | 305289 | 33921 | 7582808 | 4501733.6 | 3081074.4 | 0 | 0 | 0 | 339210 | 305289 | 33921 | Interstate Bridge | 0 | 0 | 0 | 6381340 | 3596625 | 2784715 | 0 | 0 | 0 | 0 | 0 | 0
Sven | Maintenance HQ | State Bridge |  | Ready to Advertise - On Hold | Spring 2021 Advertise | Johnson | BM20805 | VT-15 | 33 |  | bridge maintenance | 150000 | 120000 | 30000 | 7432808 | 4381733.6 | 3051074.4 | 0 | 0 | 0 | 150000 | 120000 | 30000 | State Bridge | 0 | 0 | 0 | 6381340 | 3596625 | 2784715 | 0 | 0 | 0 | 0 | 0 | 0
| District | Maintenance | To be programmed. | Completed | Could be a district fix; HOLD as BM20301 - 100% state funded project | Leicester | drain extensions | US 7 | 120 |  | Repair/Replace Down Spouts | 0 | 0 | 0 | 7432808 | 4381733.6 | 3051074.4 | 0 | 0 | 0 | 0 | 0 | 0 | Maintenance | 0 | 0 | 0 | 6381340 | 3596625 | 2784715 | 0 | 0 | 0 | 0 | 0 | 0
| Maintenance HQ | Maintenance |  | Completed | MaintHQ estimate - $100,000 / Bid estimate - $99,500; Program as BM20501 - 100% state funded project; bid 8/1/2019 | Montpelier | BM20501 | I-89 | 42N | 2018-05-25 | Replace Trough, Clean Joints | 0 | 0 | 0 | 7432808 | 4381733.6 | 3051074.4 | 0 | 0 | 0 | 0 | 0 | 0 | Maintenance | 0 | 0 | 0 | 6381340 | 3596625 | 2784715 | 0 | 0 | 0 | 0 | 0 | 0
Sven | Maintenance HQ | State Bridge |  | Completed | FY'20 FOB Project Cost and not under Maintenance; Bid 6/7/019 | New Haven | BM19503 | US 7 | 133 |  | Line existing culvert | 24186 | 19348.8 | 4837.2 | 7408622 | 4362384.8 | 3046237.2 | 0 | 0 | 0 | 24186 | 19348.8 | 4837.2 | State Bridge | 0 | 0 | 0 | 6381340 | 3596625 | 2784715 | 0 | 0 | 0 | 0 | 0 | 0
Sven | Maintenance HQ | State Bridge |  | FY22 in Vpins, advertise in spring. | ROW Clear scheduled for 1/8/21, has instream work so it cant start before July 1. FY'20 FOB Project Cost and not under Maintenance; No action required; programmed | Newport | BM19902 | VT 100 | 256 |  | Line existing culvert | 12436 | 9948.8 | 2487.2 | 7396186 | 4352436 | 3043750 | 0 | 0 | 0 | 12436 | 9948.8 | 2487.2 | State Bridge | 500000 | 400000 | 100000 | 5881340 | 3196625 | 2684715 | 0 | 0 | 0 | 500000 | 400000 | 100000
Sven | Maintenance HQ | State Bridge |  | FY22 in Vpins, advertise in spring. | Need to develop plans, permitting | Norton | BM20904 | VT-114 | 44 |  | bridge maintenance | 5000 | 4000 | 1000 | 7391186 | 4348436 | 3042750 | 0 | 0 | 0 | 5000 | 4000 | 1000 | State Bridge | 125000 | 100000 | 25000 | 5756340 | 3096625 | 2659715 | 0 | 0 | 0 | 125000 | 100000 | 25000
Kristin | Structures | Interstate Bridge | Structures to Scope |  | No action necessary for bridge maintenance; No action required; possible PDB project | Norwich |  | I-91 | 48 N&S | 2018-05-25 | Trough and concrete Repair | 0 | 0 | 0 | 7391186 | 4348436 | 3042750 | 0 | 0 | 0 | 0 | 0 | 0 | Interstate Bridge | 0 | 0 | 0 | 5756340 | 3096625 | 2659715 | 0 | 0 | 0 | 0 | 0 | 0
| Maintenance - HQ | Maintenance |  | Completed | MaintHQ estimate - $120,000 / Bid estimate - $155,000; Program as BM20404 - 100% state funded project; bid 8/19/2019 | Norwich | BM20404 | I-91 | 51 N&S |  | Replace trough/joint work | 0 | 0 | 0 | 7391186 | 4348436 | 3042750 | 0 | 0 | 0 | 0 | 0 | 0 | Maintenance | 0 | 0 | 0 | 5756340 | 3096625 | 2659715 | 0 | 0 | 0 | 0 | 0 | 0
Sven | Maintenance HQ | State Bridge |  | FY22 in Vpins, advertise in spring. | Need to develop plans, permitting | Randolph | BM20408 | VT-14 | 37 |  | bridge maintenance | 5000 | 4000 | 1000 | 7386186 | 4344436 | 3041750 | 0 | 0 | 0 | 5000 | 4000 | 1000 | State Bridge | 75000 | 60000 | 15000 | 5681340 | 3036625 | 2644715 | 0 | 0 | 0 | 75000 | 60000 | 15000
Sven | Maintenance HQ | State Bridge |  | Completed |  | Richmond | BM20504 | US-2 | 24 |  | bridge maintenance | 153661 | 122928.8 | 30732.2 | 7232525 | 4221507.2 | 3011017.8 | 0 | 0 | 0 | 153661 | 122928.8 | 30732.2 | State Bridge | 0 | 0 | 0 | 5681340 | 3036625 | 2644715 | 0 | 0 | 0 | 0 | 0 | 0
Sven | Maintenance HQ | State Bridge |  | FY22 in Vpins, advertise in spring. | Need to develop plans, permitting | Rockingham | BM20204 | US-5 | 41 |  | bridge maintenance | 4846 | 3876.8 | 969.2 | 7227679 | 4217630.4 | 3010048.6 | 0 | 0 | 0 | 4846 | 3876.8 | 969.2 | State Bridge | 100000 | 80000 | 20000 | 5581340 | 2956625 | 2624715 | 0 | 0 | 0 | 100000 | 80000 | 20000
Sven | Maintenance HQ | State Bridge |  | Completed | No action required; programmed; bid 5/24/2018 | Rutland City | BM19302 | River St. | 27 | Dist | Mill and Fill with Concrete Repair | 0 | 0 | 0 | 7227679 | 4217630.4 | 3010048.6 | 0 | 0 | 0 | 0 | 0 | 0 | State Bridge | 0 | 0 | 0 | 5581340 | 2956625 | 2624715 | 0 | 0 | 0 | 0 | 0 | 0
Sven | Maintenance HQ | State Bridge |  | FY22 in Vpins, advertise in spring. | Ready to advertise | Rutland Town | BM20301 | BRUS-4 | 4 |  | bridge maintenance | 155000 | 124000 | 31000 | 7072679 | 4093630.4 | 2979048.6 | 0 | 0 | 0 | 155000 | 124000 | 31000 | State Bridge | 0 | 0 | 0 | 5581340 | 2956625 | 2624715 | 0 | 0 | 0 | 0 | 0 | 0
Sven | Maintenance HQ | Interstate Bridge | To be programmed. | Completed | Fix leakage (not bearings); Program as BM20401 - 90%-10% funded project | Sharon | BM20401 | I-89 | 15 N&S |  | Repair vertical plate joint, clean joints | 143155 | 128839.5 | 14315.5 | 6929524 | 3964790.9 | 2964733.1 | 0 | 0 | 0 | 143155 | 128839.5 | 14315.5 | Interstate Bridge | 0 | 0 | 0 | 5581340 | 2956625 | 2624715 | 0 | 0 | 0 | 0 | 0 | 0
Sven | Maintenance - HQ | Maintenance | Awarded to Neil Daniels | Completed | MaintHQ estimate - $100,000 / Bid estimate - $125,000; Program as BM20402 - 100% state funded project | Sharon | BM20402 | I-89 | 18N |  | Replace trough, bearings | 0 | 0 | 0 | 6929524 | 3964790.9 | 2964733.1 | 0 | 0 | 0 | 0 | 0 | 0 | Maintenance | 0 | 0 | 0 | 5581340 | 2956625 | 2624715 | 0 | 0 | 0 | 0 | 0 | 0
Sven | Maintenance HQ | Maintenance | Awarded to GW Tatro | Completed | MaintHQ estimate - $80,000 / Bid estimate - $18,950; Program as BM20804 - 100% state funded project; bid 9/18/2019 | Sheldon | BM20804 | VT 78 | 16 |  | Failed wingwalls | 0 | 0 | 0 | 6929524 | 3964790.9 | 2964733.1 | 0 | 0 | 0 | 0 | 0 | 0 | Maintenance | 0 | 0 | 0 | 5581340 | 2956625 | 2624715 | 0 | 0 | 0 | 0 | 0 | 0
Sven | Maintenance HQ | Interstate Bridge | Awarded to Cold River Bridge | Completed | FY'20 FOB Project Cost and not under Maintenance; No action required; programmed' bid 8/15/2019 | Sheffield | BM19702 | I-91 | 101-2N |  | Line existing culvert | 166264 | 149637.6 | 16626.4 | 6763260 | 3815153.3 | 2948106.7 | 0 | 0 | 0 | 166264 | 149637.6 | 16626.4 | Interstate Bridge | 0 | 0 | 0 | 5581340 | 2956625 | 2624715 | 0 | 0 | 0 | 0 | 0 | 0
Sven | Maintenance HQ | Interstate Bridge |  | Awarded | NTP issed 12/15//20 | So. Burlington | BM20503 | I-89 | 70 N/S |  | bridge maintenance | 304917 | 274425.3 | 30491.7 | 6458343 | 3540728 | 2917615 | 0 | 0 | 0 | 304917 | 274425.3 | 30491.7 | Interstate Bridge | 0 | 0 | 0 | 5581340 | 2956625 | 2624715 | 0 | 0 | 0 | 0 | 0 | 0
Kristin | Structures | Interstate Bridge | Structures to Scope |  | Currently D&E Project; district to shore beam as an interim action; No action required; PDB candidate project | Springfield | IM 091-1(83) | I-91 | 28N | 2018-06-10 | Programmed (no longer considered bridge maintenance) | 0 | 0 | 0 | 6458343 | 3540728 | 2917615 | 0 | 0 | 0 | 0 | 0 | 0 | Interstate Bridge | 0 | 0 | 0 | 5581340 | 2956625 | 2624715 | 0 | 0 | 0 | 0 | 0 | 0
Sven | Structures | Interstate Bridge | Awarded to ECI | Completed | Sven/Jeremy to move forward; No action required; programmed; bid 7/17/2020 | Springfield | BM19204 | I-91 / US 5 | 25 N&S / 43A | 2018-06-28 | Replace/eliminate joints and repair bridge seats | 768868 | 691981.2 | 76886.8 | 5689475 | 2848746.8 | 2840728.2 | 0 | 0 | 0 | 768868 | 691981.2 | 76886.8 | Interstate Bridge | 0 | 0 | 0 | 5581340 | 2956625 | 2624715 | 0 | 0 | 0 | 0 | 0 | 0
Sven | Maintenance HQ | State Bridge |  | FY22 may have to go to structures | waiting to hear back from stream alteration/fisheries if the existing culvert can be lined. May have to punt to structures for replacement | Springfield | BM19201 | VT 106 | 4 |  | Reinforced concrete invert | 7599 | 6079.2 | 1519.8 | 5681876 | 2842667.6 | 2839208.4 | 0 | 0 | 0 | 7599 | 6079.2 | 1519.8 | State Bridge | 200000 | 160000 | 40000 | 5381340 | 2796625 | 2584715 | 0 | 0 | 0 | 200000 | 160000 | 40000
| Maintenance HQ | State Bridge | Project federalized and now funded under SHB | Ready to Advertise - On Hold | Spring 2021 Advertise MaintHQ estimate - $225,000 / Bid estimate - $604,631 *rejected; Program as BM20802 - 100% state funded project | St. Albans | BM20802 | VT 104 | 20 | 2018-07-19 | Replace Joint and Trough | 250000 | 200000 | 50000 | 5431876 | 2642667.6 | 2789208.4 | 0 | 0 | 0 | 250000 | 200000 | 50000 | State Bridge | 0 | 0 | 0 | 5381340 | 2796625 | 2584715 | 0 | 0 | 0 | 0 | 0 | 0
| Maintenance - HQ | Maintenance | Awarded to Neil Daniels | Completed | MaintHQ estimate - $140,000 / Bid estimate - $93,500; Program as BM20803 - 100% state funded project; bid 8/5/2019 | St. Albans | BM20803 | VT 105 / I-89 | 1 / 91 |  | Joint and joint drainage system repairs | 0 | 0 | 0 | 5431876 | 2642667.6 | 2789208.4 | 0 | 0 | 0 | 0 | 0 | 0 | Maintenance | 0 | 0 | 0 | 5381340 | 2796625 | 2584715 | 0 | 0 | 0 | 0 | 0 | 0
Sven | Maintenance HQ | Maintenance |  |  | assumed amount for tracking purpose; per Sven | Statewide - Miscellaneous | n/a |  |  |  | Miscellaneous charges to MVT-073 for materials | 50000 | 0 | 50000 | 5381876 | 2642667.6 | 2739208.4 | 50000 | 0 | 50000 | 0 | 0 | 0 | Maintenance | 50000 | 0 | 50000 | 5331340 | 2796625 | 2534715 | 50000 | 0 | 50000 | 0 | 0 | 0
Sven | Maintenance HQ | Maintenance |  |  | assumed amount for tracking purpose | Statewide - Operating Expenses | n/a |  |  |  | Maintenance expenditures for vehicles, phones, etc. | 50000 | 0 | 50000 | 5331876 | 2642667.6 | 2689208.4 | 50000 | 0 | 50000 | 0 | 0 | 0 | Maintenance | 50000 | 0 | 50000 | 5281340 | 2796625 | 2484715 | 50000 | 0 | 50000 | 0 | 0 | 0
Sven | Maintenance HQ | Maintenance |  |  | assumed amount for tracking purpose | Statewide - Paint Program | n/a |  |  |  | Maintenance paint program | 0 | 0 | 0 | 5331876 | 2642667.6 | 2689208.4 | 0 | 0 | 0 | 0 | 0 | 0 | Maintenance | 0 | 0 | 0 | 5281340 | 2796625 | 2484715 | 0 | 0 | 0 | 0 | 0 | 0
Districts | Maintenance HQ | Maintenance |  |  | assumed amount for tracking purpose | Statewide - Washing Program | n/a |  |  |  | Maintenance bridge cleaning and washing program | 0 | 0 | 0 | 5331876 | 2642667.6 | 2689208.4 | 0 | 0 | 0 | 0 | 0 | 0 | Maintenance | 0 | 0 | 0 | 5281340 | 2796625 | 2484715 | 0 | 0 | 0 | 0 | 0 | 0
Districts | Maintenance HQ | Maintenance |  |  | assumed amount for tracking purpose | Statewide - Applying Preservation Materials Program | n/a |  |  |  | Maintenance bridge application of preservation material program | 0 | 0 | 0 | 5331876 | 2642667.6 | 2689208.4 | 0 | 0 | 0 | 0 | 0 | 0 | Maintenance | 0 | 0 | 0 | 5281340 | 2796625 | 2484715 | 0 | 0 | 0 | 0 | 0 | 0
Sven | Maintenance HQ | State Bridge |  | FY22 in Vpins, advertise in spring. | Plans sent to stream alteration for informal review. once design has been blessed will finish design and submit for permitting and final hydraulics | Sunderland | BM20102 | US-7 | 19-5 |  | bridge maintenance | 5000 | 4000 | 1000 | 5326876 | 2638667.6 | 2688208.4 | 0 | 0 | 0 | 5000 | 4000 | 1000 | State Bridge | 0 | 0 | 0 | 5281340 | 2796625 | 2484715 | 0 | 0 | 0 | 0 | 0 | 0
Sven | Maintenance HQ | State Bridge |  | FY22 in Vpins, advertise in spring. | Ready to advertise | Underhill | BM20505 | VT-15 | 12 |  | bridge maintenance | 130000 | 104000 | 26000 | 5196876 | 2534667.6 | 2662208.4 | 0 | 0 | 0 | 130000 | 104000 | 26000 | State Bridge | 0 | 0 | 0 | 5281340 | 2796625 | 2484715 | 0 | 0 | 0 | 0 | 0 | 0
| Maintenance - HQ | Maintenance | To be programmed. |  | Could be a district fix; HOLD as BM20302 - 100% state funded project | Wallingford | ON HOLD | VT 103 | 49 |  | Concrete Repair | 0 | 0 | 0 | 5196876 | 2534667.6 | 2662208.4 | 0 | 0 | 0 | 0 | 0 | 0 | Maintenance | 0 | 0 | 0 | 5281340 | 2796625 | 2484715 | 0 | 0 | 0 | 0 | 0 | 0
Sven | Maintenance HQ | Interstate Bridge |  | Awarded | Completion date 6/11/21 | Waterbury | BM20507 | I-89 | 50 |  | bridge maintenance | 225000 | 202500 | 22500 | 4971876 | 2332167.6 | 2639708.4 | 0 | 0 | 0 | 225000 | 202500 | 22500 | Interstate Bridge | 0 | 0 | 0 | 5281340 | 2796625 | 2484715 | 0 | 0 | 0 | 0 | 0 | 0
| Maintenance HQ | State Bridge |  | Completed | Program as BM20201 - 80%-20% funded project; bid 4/28/2020 | Weathersfield | BM20201 | VT 106 | 8 | 2017-06-21 | Membrane and Pave, replace Joint and Trough | 325061 | 260048.8 | 65012.2 | 4646815 | 2072118.8 | 2574696.2 | 0 | 0 | 0 | 325061 | 260048.8 | 65012.2 | State Bridge | 0 | 0 | 0 | 5281340 | 2796625 | 2484715 | 0 | 0 | 0 | 0 | 0 | 0
Sven | Maintenance HQ | Interstate Bridge |  | FY22 in Vpins, advertise in spring. | Need to develop plans, permitting | Westminster | BM20203 | I-91 | 19 |  | bridge maintenance | 5000 | 4500 | 500 | 4641815 | 2067618.8 | 2574196.2 | 0 | 0 | 0 | 5000 | 4500 | 500 | Interstate Bridge | 225000 | 202500 | 22500 | 5056340 | 2594125 | 2462215 | 0 | 0 | 0 | 225000 | 202500 | 22500
| Maintenance HQ | Maintenance |  | Completed | MaintHQ estimate - $150,000 / Bid estimate - $176,532; Program as BM20403 - 100% state funded project; substantial completion 11/1/2019 | Williamstown | BM20403 | I-89 | 35N | 2018-07-16 | Repair bridge seat, abutment and trough | 0 | 0 | 0 | 4641815 | 2067618.8 | 2574196.2 | 0 | 0 | 0 | 0 | 0 | 0 | Maintenance | 0 | 0 | 0 | 5056340 | 2594125 | 2462215 | 0 | 0 | 0 | 0 | 0 | 0
Sven | Maintenance HQ | State Bridge |  | Completed |  | Williamstown | BM20406 | VT-14 | 60 |  | bridge maintenance | 155000 | 124000 | 31000 | 4486815 | 1943618.8 | 2543196.2 | 0 | 0 | 0 | 155000 | 124000 | 31000 | State Bridge | 0 | 0 | 0 | 5056340 | 2594125 | 2462215 | 0 | 0 | 0 | 0 | 0 | 0
| Structures | State Bridge |  | Completed | Emergent Need MaintHQ estimate - $247,983 / Bid estimate - $70,250; Program as BM20202 - 100% state funded project (per Wayne S); acceptance 11/18/2019 | Vernon | BM20202 | VT 142 | 35N |  | Repair beam ends only; no capacity strengthening | 0 | 0 | 0 | 4486815 | 1943618.8 | 2543196.2 | 0 | 0 | 0 | 0 | 0 | 0 | State Bridge | 0 | 0 | 0 | 5056340 | 2594125 | 2462215 | 0 | 0 | 0 | 0 | 0 | 0
| Structures | State Bridge | Awarded to Filskov Bros. | Completed | Emergent Need; Program as STP CULV(63) - 100% state funded project; substantial completion 11/2/2019 | Wells | STP CULV(63) | VT 30 | 83 |  | Replace failed culvert with state precast boxes | 16800 | 0 | 16800 | 4470015 | 1943618.8 | 2526396.2 | 0 | 0 | 0 | 16800 | 0 | 16800 | State Bridge | 0 | 0 | 0 | 5056340 | 2594125 | 2462215 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | Committed Totals → | 6443263 | 5443881.2 | 999381.8 |  |  |  | 100000 | 0 | 100000 | 6343263 | 5443881.2 | 899381.8 | Committed Totals → | 2153188 | 1652500 | 500688 |  |  |  | 100000 | 0 | 100000 | 2053188 | 1652500 | 400688
[18 empty] | Maintenance Appropriation Total |  |  | PDB Bridge Appropriation Total | [9 empty] | Maintenance Appropriation Total |  |  | PDB Bridge Appropriation Total
[17 empty] | Total | 2103278 | 0 | 2103278 | 8810000 | 7387500 | 1422500 | [6 empty] | Total | 2103278 | 0 | 2103278 | 5106250 | 4246625 | 859625
[17 empty] | Balance | 2003278 | 0 | 2003278 | 2466737 | 1943618.8 | 523118.2 | [6 empty] | Balance | 2003278 | 0 | 2003278 | 3053062 | 2594125 | 458937

## Potentials
Pending 2020 Projects | [11 empty] | Potential to Advance and Spend FY'21 Funds
Town ¦ Project Number | Route | Bridge Number | Note | Estimate | SFY'21 Estimate | Federal Share | State Share | SFY'22 Estimate | BIF Deadline | BIF Date | District Need Date | Group Comments
Barton BM20903 | I-91 | Br105-1 |  | 105000 | 5000 | 4500 | 500 | 100000 |  |  |  | currently out for permits (anticipated Mar. 2021)
Berlin BM20701 | VT-12 | Br64 | failed wingwall | 105000 | 5000 | 4000 | 1000 | 100000 |  |  |  | still need to design and permit
Bloomfield BM20902 | VT-102 | Br9 | pending FHWA approval and advertisement | 130000 | 130000 | 104000 | 26000 | 0 |  |  |  | ready to advertise
Clarendon BM20302 | US-7 | Br90N&S | Jeremy increased the cost which has not yet been updated in VPINs | 105000 | 105000 | 84000 | 21000 | 0 |  |  |  | ready to advertise; could advance to spend FY'21
Derby BM20905 | VT-191 | Br1 | pending FHWA approval and advertisement for spring 2021 | 530000 | 530000 | 424000 | 106000 | 0 |  |  |  | ready to advertise; could spend some FY'21 funds
Essex BM19501 | VT-128 | Br1 |  | 530000 | 30000 | 24000 | 6000 | 500000 |  |  |  | waiting on NEPA re-evaluation (FY'22)
Glover BM20901 | VT-16 | Br19 |  | 180000 | 180000 | 144000 | 36000 | 0 |  |  |  | ready to advertise; could advance to spend FY'21
Granville BM20407 | VT-100 | Br159 | failed wingwall | 105000 | 5000 | 4000 | 1000 | 100000 |  |  |  | still need to design and permit
Johnson BM20805 | VT-15 | 33 |  | 150000 | 150000 | 120000 | 30000 | 0 |  |  |  | ready to advertise; could advance to spend FY'21
Newport BM19902 | VT-100 | Br256 | liner | 530000 | 30000 | 24000 | 6000 | 500000 |  |  |  | waiting on ROW clear (FY'22)
Norton BM20904 | VT-114 | Br44 | failed wingwall | 130000 | 5000 | 4000 | 1000 | 125000 |  |  |  | still need to design and permit
Randolph BM20408 | VT-14 | Br37 |  | 80000 | 5000 | 4000 | 1000 | 75000 |  |  |  | still need to design and permit
Rockingham BM20204 | US-5 | Br41 | failed wingwall | 105000 | 5000 | 4000 | 1000 | 100000 |  |  |  | still need to design and permit
Rutland Town BM20301 | BRUS-4 | Br4-4 |  | 155000 | 155000 | 124000 | 31000 | 0 |  |  |  | ready to advertise; could advance to spend FY'21
Springfield BM19201 | VT-106 | Br4 | liner | 220000 | 20000 | 16000 | 4000 | 200000 |  |  |  | waiting on stream alteration /fisheries; pushing for replacement
St. Albans BM20802 | VT-104 | Br20 |  | 250000 | 250000 | 200000 | 50000 | 0 |  |  |  | ready to advertise; could advance to spend FY'21
Sunderland BM20102 | US-7 | Br19-5 | liner - check this as there is no expected cost for FY22 and jumps to FY23 | 205000 | 5000 | 4000 | 1000 | 0 |  |  |  | still need to design and permit
Underhill BM20505 | VT-15 | Br12 | this project is going out in CY2020 and will encase the backwall and wingwall (Sven's note) | 130000 | 130000 | 104000 | 26000 | 0 |  |  |  | ready to advertise; could advance to spend FY'21
Westminster BM20203 | I-91 | Br19/D19 |  | 230000 | 5000 | 4500 | 500 | 225000 |  |  |  | still need to design and permit
Total = |  |  |  |  | 1750000 | 1401000 | 349000 | 2025000
Potential 2020 Projects | [11 empty] | Potential to Advance and Spend FY'21 Funds
Town ¦ Project Number | Route | Bridge Number | Note | Estimate | SFY'22 Estimate | Federal Share | State Share | SFY'22 Estimate | BIF Deadline | BIF Date | District Need Date | Group Comments
Andover | VT-11 | Br36 | should have been fixed during paving project, believe it wasn't though (Sven's note) | 125000 |  |  |  |  | 2020-06-01 | 2019-07-29
Barton | US-5 | Br162 (BIF) | district planned to chip out bad concrete and pour new concrete prior to winter (2020) but this is located in a class 1 section of US-5 and town owned and maintained | [8 empty] | completed, not considered as a priority to advance, or should be compete for a rehabilitation /replacement type project
Bennington | VT-279 | Br1 | joint tight with possible MSE wall movement (plan is to monitor) | [8 empty] | completed, not considered as a priority to advance, or should be compete for a rehabilitation /replacement type project
Berlin (Riverton) | VT-12 | Br67 | district dealing with bad deck that rates ok, narrow road (Sven's note) (being considered for PDB programming) | 170000 | [6 empty] | 2020 | completed, not considered as a priority to advance, or should be compete for a rehabilitation /replacement type project
Brattleboro | I-91 /VT-9 | Br7 / Br54A at exit 2 | only westbound lane was done; proposing to hydromill the eastbound lane under a change order of the existing project - Kristin to discuss with Matt D. (FHWA) | 800000 | 800000 | 0 | 800000 |  |  |  |  | BM19203; milling of existing pavement, concrete deck repair, installing new membrane, re-paving, and other related work
Bridgewater | US-4 | Br38 | loose joint - fixed by the district /bridge crew (this was completed) | [8 empty] | completed, not considered as a priority to advance, or should be compete for a rehabilitation /replacement type project
Bridgewater | US-4 | Br45 | pier cap issues to be fixed by the district /bridge crew (spring 2021) (bridge crew doesn't have the capacity to do this) | 100000 | 100000 | 0 | 100000 |  |  |  |  | low priority (no BIF) - fixing a popout of concrete on a pier cap with no in-stream work anticipated
Brookfield | I-89 | Br34N | district did a temporary patch with a plan to repair (this was completed) | [8 empty] | completed, not considered as a priority to advance, or should be compete for a rehabilitation /replacement type project
Cambridge | private | Gates CovBr | discussions underway for possible project /stabilization (decision made to program as a PDB project) | 150000 | [5 empty] | 2020-03-26 |  | completed, not considered as a priority to advance, or should be compete for a rehabilitation /replacement type project
Castleton (BIF) | [11 empty] | medium priority
Chester | VT-11 | Br44 | should have been fixed during paving project, believe it wasn't though (Sven's note) | 250000 |  |  |  |  | 2020-06-01 | 2019-07-29
Colchester / So. Burlington | I-89 | Br70S | Josh Hulett brought up header issues during paving project summer (Sven's note) | 150000 | [6 empty] | 2020 | low priority (no BIF) - fixed (possibly flooded with plug joint material) as part of the paving project
Derby | I-91 | Br110N&S (BIF) | failed trough and associated concrete repair | 300000 | 300000 | 0 | 300000 |  |  | 2020-07-23 |  | medium priority - great potential to repair
Eden | VT-100 | Br220 | full depth hole (2020) steel plate added (short term fix) | 150000 | [7 empty] | low priority - continue to monitor for future PDB project
Essex | VT-117 | Br2 | district monitoring until project goes (concrete slabs bridging over failing culvert) (this is a planned PDB project) | [8 empty] | completed, not considered as a priority to advance, or should be compete for a rehabilitation /replacement type project
Essex | VT-15 | Br2 | 2’x2’ hole - crew covered the hole with plywood, fill back to road grade, and abandon the planned fix | 110000 | [7 empty] | low priority
Essex | VT-289 | Br13 | J. Dieser contacted about bridge and approach pavement issues (Sven's note - district repaired this) | 60000 | [6 empty] | 2020 | district has shimmed this and addressed the problem
Fairlee | I-91 | Br55-2 (BIF) | pending hydraulic input (likely a PDB project)
Fairlee | I-91 | Br55-3 (BIF) | pending hydraulic input (likely a PDB project)
Goshen | VT-73 | Br9 | fascia deterioration and repair needed (short structure) | 130000 | 130000 | 0 | 130000 |  |  |  | 2020 | medium priority - has potential to impact traffic if deterioration continues
Hartford | I-91 | Br46 (BIF) | programmed (IDIQ project) | [8 empty] | completed, not considered as a priority to advance, or should be compete for a rehabilitation /replacement type project
Hartford | I-91 | Br47N&S (BIF) | backwall deterioration and hole | 300000 | 300000 | 0 | 300000 |  |  | 2020-06-16 |  | medium priority - great potential to repair
Hartland | VT-12 | Br3 | emergency need and waiting on FHWA approval for EA (PDB project and allowed force account work - emergent need) | [8 empty] | completed, not considered as a priority to advance, or should be compete for a rehabilitation /replacement type project
Londonderry | VT-100 | Br90 | hole in the deck and deterioration - pavement showing signs of deck issues | 100000 | [6 empty] | 2020 | low priority - district has performed extensive repair to sections of the deck
Lunenburg | US-2 | Br123 | keystone movement (proposed for PDB project) | 350000 |  |  |  |  | 2020-09-01 | 2019-10-17 |  | completed, not considered as a priority to advance, or should be compete for a rehabilitation /replacement type project
Middlebury | VT-116 | Br4 | (district completed repairs using MVT-073 funding from Sven) | [8 empty] | completed, not considered as a priority to advance, or should be compete for a rehabilitation /replacement type project
Milton | I-89 | Br81N&S | compression seals have failed and contractor is past warranty (Sven's note) (project accepted 1/10/2020) | 200000 | [6 empty] | 2020 | medium priority - need to reach out to the manufacturer to the compression seal for repair / replacement options
Moretown | VT-100B | Br3 | sidewalk hole - repair planned by the district /bridge crew (this was completed) | [8 empty] | completed, not considered as a priority to advance, or should be compete for a rehabilitation /replacement type project
New Haven | US-7 | Br129 | approach settlement which district has addressed (this was completed) | [8 empty] | completed, not considered as a priority to advance, or should be compete for a rehabilitation /replacement type project
North Hero | US-2 | Br5 | hole in the deck repaired by the district /bridge crew (fall 2020) - programmed project (short term completed) (this is a PDB project) | [8 empty] | completed, not considered as a priority to advance, or should be compete for a rehabilitation /replacement type project
Norton | VT-114 | Br41 | flowable fill installed, still voids remaining, estimate may be low for replacement (Sven's note) | 500000 | [6 empty] | 2019 | low priority - continue to monitor for signs of material loss, settlement, etc.
Pittsford | US-7 | Br108 | (PDB programmed project) | 200000 |  |  |  |  | 2020-05-01 | 2019-07-23 |  | completed, not considered as a priority to advance, or should be compete for a rehabilitation /replacement type project
Plymouth | VT-100A | Br10 | installed steel plate over holes (permanent repair planned but did not happen) | [8 empty] | low priority - areas next to repair are considered poor concrete - plates are still on the bridge an secure
Randolph | I-89 /VT-66 |  | trough repair /replacement project | 130000 | 130000 | 0 | 130000
Richmond | I-89 | Br58N | Josh Hulett brought up header issues during paving project summer (Sven's note) | 150000 | [6 empty] | 2020 | bridge joints were shimmed as part of the paving project and considered to have been addressed
Richmond | I-89 | Br59N | Josh Hulett brought up header issues during paving project summer (Sven's note) | 150000 | [6 empty] | 2020 | bridge joints were shimmed as part of the paving project and considered to have been addressed
Rockingham | I-91 | Br22N&S (BIF) | vertical restriction signs needed (signs installed and confirmed 9/14/2020) | [8 empty] | completed, not considered as a priority to advance, or should be compete for a rehabilitation /replacement type project
Rockingham | I-91 | Br23S (BIF) | bearing repair or replacement | 200000 | 200000 | 0 | 200000 |  | this year | 2020-06-16 |  | medium priority
Rutland City | River Street | Br27 | hole in the approach - repaired by the district /bridge crew (potential for future PDB project) | [8 empty] | completed, not considered as a priority to advance, or should be compete for a rehabilitation /replacement type project
Sharon | I-89 | Br14 | worked was performed by the district, repairing the spalling on the driving surface in CY2019 (Sven's note)
Sharon | I-89 | Br16N&S | abutment/joints/troughs - needs NB trough; finger joints ride hard /differential elevation, also bridge seat and bearing work; bridge crew had wanted to jack at one point (Sven's note) | 350000 | 350000 | 0 | 350000 |  |  |  | 2019 | Sven / Jeremy to look into these and determine if the need remains or work was done
Sharon | I-89 | Br17N&S | failed troughs at both abutments; finger joints have elevation issues leading to a large bump entering the bridge, drawn a lot of comments over the years (Sven's note) | [6 empty] | 7/17/2018
Sharon | I-89 | Br19 | district to perform concrete repairs (double barrel box with wearing surface issues) | [8 empty] | low priority - Sven to ask Nick if repairs were made
Sheldon | VT-105 | Br10 | bearing seat deterioration (Sven's note) | 175000 | [6 empty] | 2019 | low priority (no BIF) - condition or concern brought up by bridge crew
Springfield | I-91 | Br26N&S (BIF) | backwall deterioration with leakage from joints (evaluating to be done as part of the br28N/S project) | 350000 |  |  |  |  | this year | 2020-06-16
Springfield | I-91 | Br28N | district to remove loose fascia concrete and reinstall wood shoring (PDB programmed project) | [8 empty] | completed, not considered as a priority to advance, or should be compete for a rehabilitation /replacement type project
Springfield | I-91 | Br28S (BIF) | district to consult with Sven on action items to repair hole in the deck (PDB programmed project) | [8 empty] | completed, not considered as a priority to advance, or should be compete for a rehabilitation /replacement type project
Springfield | metal bin wall | under I-91, Br27N&S | district planning temporary repair/stabiliation (spring 2021) but will need replacement (evaluating to be done as part of the br28N/S project)
St. Johnsbury | I-91 | Br91S | work accomplished by district using MVT funds | [8 empty] | completed, not considered as a priority to advance, or should be compete for a rehabilitation /replacement type project
Tunbridge | VT-110 | Br5 | reported by district as in poor condition and undersized (to compete with other bridges) | [8 empty] | to compete for a potential for PDB project
Underhill | VT-15 | Br12 | substructure spalling and hole with bridge deck spalling, exposed rehab, and delams (BM20505 programmed project; bridge crew did immediate need repairs in 2018) | [8 empty] | completed, not considered as a priority to advance, or should be compete for a rehabilitation /replacement type project
Underhill | VT-15 | Br14 | spalling on concrete box walls, wing work (Sven's note) | 100000 | [6 empty] | 2019 | Sven to ask Jody if repairs were made; update - repairs were not made and action is to monitor
Waterford | I-93 | Br1S (BIF) | work accomplished by district using MVT funds to address void under abutment 2 (this was completed) | [8 empty] | completed, not considered as a priority to advance, or should be compete for a rehabilitation /replacement type project
Whitingham | VT-100 | Br38 | (possibly done by district - per Craig B. the work needed to address the BIF was completed) | [6 empty] | 2018-03-17
Winooski | I-89 | Br72N | joint issues - temporary bunking repair installed by the district /bridge crew (Sven confirmed by email) | [8 empty] | completed, not considered as a priority to advance, or should be compete for a rehabilitation /replacement type project
Total = |  |  |  | 5750000 | 2310000 | 0 | 2310000 | 0