## AllNeeds
ID no. | Town | Other towns | Location notes | Need/ Concern | Need theme | Next Steps | Lead Implementer | Opportunities for Collaboration | Timeframe | Approx. Cost (if known) | Funding Options (if blank, goes through normal VTrans programs) | Begin Milemarker (End to End) | To Milemarker (End to End) | Begin Milemarker (Town based) | To Milemarker (Town based)
3079 | Bennington | All towns | Corridor wide | Study effectiveness of chain up areas on Route 9 | Study effectiveness of chain up areas | Study the effectiveness of chain up areas on Route 9 | VTrans (Highway Safety, Planning) | DMV | Short Term (1-5 years) |  |  | 5.8 | 43.297 | 5.8 | 5.851
3095 | Bennington | All towns | Corridor wide | Emerald Ash Borer is an emerging issue in Vermont and will create hazardous trees within the ROW. | Evaluate mowing practices and/or vegetation management | Monitor spread of Emerald Ash Borer and follow VTrans Maintenance District Hazard Tree Cutting Environmental Standard Operating Procedure. | VTrans (District, Environmental) |  | Short Term (1-5 years) |  |  | 5.8 | 43.297 | 5.8 | 5.851
3096 | Bennington | All towns | Corridor wide | Increasing protections for the Monarch Butterfly and its habitat is a potential issue that needs to be addressed. | Evaluate mowing practices and/or vegetation management | Continue to work on participation in the Monarch Candidate Conservation Agreement and refine best management and designa practices that can be implemented as part of this agreement. | VTrans (Environmental) |  | Short Term (1-5 years) |  |  | 5.8 | 43.297 | 5.8 | 5.851
3102 | Bennington | All towns | Corridor wide | Signage for recreation areas along the corridor are inconsistent and not always easily interpreted at the prevailing speed. | Evaluate signage and/or road markings | Evaluate the location of recreation signs along the Corridor to see if existing sign locations can be optimized. Looking further forward, create a plan for recreation signage along the Corridor. | VTrans (Traffic Operations) | ANR (Forest, Parks and Recreation), Vermont Dept of Tourism and Marketing, WRC, BCRC | Short Term (1-5 years) |  |  | 5.8 | 43.297 | 5.8 | 5.851
3110 | Bennington | All towns | Corridor wide | Explore adding warnings about poor weather conditions and traffic interruptions along the corridor. Install electronic message sign that warns of winter conditions at higher elevations along the travel corridor. | Improve travel information | Develop a corridor wide traffic management plan that includes parts of Route 100 to the ski resorts. Explore adding additional electronic messaging about poor weather conditions and traffic interruptions. | VTrans (Traffic Signal Operations & ITS) | Towns, Police, Mt Snow Ski Resort | Short Term (1-5 years) | Low ($0 - $100,000) |  | 5.8 | 43.297 | 5.8 | 5.851
3112 | Bennington | All towns | Corridor wide | Improve sweeping plan, including shoulders, to improve travel conditions for bicyclists. | Improve sweeping plan | When sweeping plan is next revised, consider shoulder sweeping and the needs of bicyclists. | VTrans (District) |  | Short Term (1-5 years) | Low ($0 - $100,000) |  | 5.8 | 43.297 | 5.8 | 5.851
3120 | Bennington | All towns | Corridor wide | Wild parsnip, wild churvill, Japanese knotweed and other invasive plant species are spreading along the Corridor. Mowing operations may contribute to the spreading of the invasives as well as lack of invasive plant management from adjoining properties to the State ROW where some of these invasives may be originating from. Next steps: Follow the VTrans Vegetation Management Practices to reduce spread of invasive plant species such as wild parsnip, wild churvill and Japanese knotweed. For more information visit https://vtrans.vermont.gov/operations/technical-services/environmental/vegetation-management and https://vtrans.vermont.gov/operations/technical-services/environmental/best-management-practices | Evaluate mowing practices and/or vegetation management | Follow the VTrans Vegetation Management Practices to reduce spread of invasive plant species such as wild parsnip, wild churvill and Japanese knotweed. | VTrans (District and Environmental) |  | Short Term (1-5 years) | Low ($0 - $100,000) |  | 5.8 | 43.297 | 5.8 | 5.851
3121 | Bennington | All towns | Corridor wide | Study truck usage along the corridor, particularly oversized loads. Truck traffic appears to be heavy, with too many wide loads, many trucks speeding and creating notable noise by Jake brake usage. | Explore truck usage | Study truck usage along the corridor, particularly oversized loads. | VTrans (Planning, DMV, Safety) |  | Short Term (1-5 years) |  |  | 5.8 | 43.297 | 5.8 | 5.851
3073 | Woodford |  | Pull offs near townline, east of Furnace Grove Rd | The pull offs near a swimming hole and hiking trails are becoming a safety issue | Improve safety near recreation area | Coordinate with ANR (FPR) to look for solutions to the emerging parking and safety issues. Evaluate need for signage warning about pedestrians in the roadway. Coordinate with 3002, 3006 and 3072? | BCRC | ANR (Forest, Parks and Recreation), BCRC, WRC, VTrans (District, Traffic Operations, Planning) | Short Term (1-5 years) |  |  | 6.958 | -1 | 0.089 | 0
3115 | Woodford |  | East of Old Harbor Road | Crash pattern identified by VTrans staff with next steps suggested - utility pole delineation and possible relocation. | Improve roadway safety (section or intersection) | The delineation of the utility pole would be beneficial, with a delineator in front of the pole or a type-3 object marker. Relocation of the pole should be considered. | VTrans (District) | Utility company | Short Term (1-5 years) | Low ($0 - $100,000) |  | 8.429 | -1 | 1.56
3072 | Woodford |  | Long Trail/ AT crossing north of Notch Rd | The Long Trail/ Appalachian Trail crossing is becoming an increasing safety risk due to increased usage | Improve safety near recreation area | Begin coordination effort with partners to evaluate the current location of trail crossing, measures to improve safety and whether opportunities exist to move the trail crossing to a safer location in the future. Coordinate with 3002, 3006 and 3073? | BCRC | ANR (Forest, Parks and Recreation), Green Mountain National Forest, Green Mountain Club, BCRC, WRC, VTrans (Traffic Operations, District, Planning) | Short Term (1-5 years) |  |  | 9.45 | -1 | 2.581 | 0
3001 | Woodford |  | Rock cut near truck escape route | Safety concerns in this rock cut/ curves with crash records and safety analysis completed. There is a programmed project associated with the ledge issue with anticipated construction in 2021 or 2022. Other safety improvements may still be needed afterwards - including curve sign with advisory speed, high friction surface treatment and superelevation evaluation. | Improve roadway safety (section or intersection) | There is a programmed project associated with the ledge issue with anticipated construction in 2021 or 2022 - NH 010-1(51) - https://resources.vtrans.vermont.gov/factsheet/default.aspx?pin=13B350 | VTrans (Project Manager is Bruce Martin) |  | Short Term (1-5 years) | High ($1 million - $10 million) | Already programmed and funded | 9.799 | -1 | 2.93 | -1
3002 | Woodford |  | Woodford State Park | Safety and snow removal issues for people accessing Woodford State Park who may need to cross Route 9, particularly in the winter when parking is located on the other side of the street. | Improve safety near recreation area | Coordinate between stakeholders to look for solutions to the emerging parking, snow removal and safety issues. Evaluate need for signage warning about pedestrians in the roadway. Coordinate with 3006, 3072 and 3073? | BCRC | ANR (Forest, Parks and Recreation), BCRC, WRC, VTrans (District, Traffic Operations, Planning) | Short Term (1-5 years) | Low ($0 - $100,000) |  | 15.021 | -1 | 8.152 | -1
3020 | Searsburg |  | Bridge 20 | The location of the Searsburg Bridge 20 Project is an important connection for aquatic and terrestrial animal passage (including large mammals). VTrans has been working with ANR and will be considerably upzing the structure. It is due to be constructed in 2022. Information about the project is available at https://resources.vtrans.vermont.gov/factsheet/default.aspx?pin=13B332 | Consider accommodating wildlife when rehabilitating or replacing structure | The culvert is due to be upgraded to a bridge in 2024 in a programmed project - BF 010-1(50) - more information at https://resources.vtrans.vermont.gov/factsheet/default.aspx?pin=13B332 | VTrans (Project Manager is Nick Wark) |  | Short Term (1-5 years) | High ($1 million - $10 million) |  | 17.094 | -1 | 0.65 | 0
3031 | Searsburg |  | Route 8 intersection | Route 8 intersection has sight distance issues. Traffic turning left from a climbing lane also adds complexity to the intersection. | Improve sight distances at intersection | Evaluate which solutions are preferred to address the issue. If turn lane, look to harmonize into future paving project. If new signal or roundabout, look for funding to address the issue. | VTrans (Traffic Operations) |  | Short Term (1-5 years) |  |  | 18.265 | -1 | 1.821 | -1
3132 | Searsburg |  | East of Route 8 | Crash pattern identified by VTrans staff with next steps suggested - evaluate winter maintenance. | Improve roadway safety (section or intersection) | Evaluate winter maintenance | VTrans (District) |  | Short Term (1-5 years) |  |  | 18.499 | -1 | 2.055 | 0
3043 | Wilmington | Searsburg | Reservoir to Line Lane | Threatened plant species can be found in this area. ANR recommends stopping mowing to protect the plant. VTrans staff will have to balance against operational needs such as sight distances, hazard trees, shade on roadway, etc. | Evaluate mowing practices and/or vegetation management | VTrans District and ANR staff to discuss maintenance and mowing practices to evaluate where practices may be altered | VTrans (District) | ANR | Short Term (1-5 years) |  |  | 20.883 | 22.718 | 4.439 | 0.736
3013 | Wilmington |  | Western side of Wilmington Village | The box culvert has failing wingwalls that is causing the shoulder to fail | Improve condition of culvert and shoulder | Await culvert condition to be flagged through VTrans Asset Management Systems. | VTrans (Asset Management and District) |  | Short Term (1-5 years) | Medium ($100,000 - $1 million) |  | 23.744 | -1 | 1.76 | -1
3131 | Wilmington |  | Haystack Road | Travelers are using local roads to cut through to Route 100, Dover and the ski areas from the west during peak travel times. | Evaluate signage and/or road markings | Set up a meeting to discuss issues and explore opportunities on State and Town highways. See Augur Hill Road example for potential options. | VTrans (Traffic Operations) | Town of Wilmington, WRC | Short Term (1-5 years) | Low ($0 - $100,000) |  | 23.887 | -1 | 1.905 | 0
3109 | Wilmington |  | 53 West Main St to Country Club Road | Area was evaluated for potential to convert to class 1 town highway in 2015 for benefits relating to design flexibility and snow removal, but was considered too expensive. Consider re-evaluating periodically . | Develop Roadway Master Plan for this section | Develop Roadway Master Plan for this section, focusing on crash patterns, drainage and parking. Periodically evaluate potential to convert to class 1 town highway. Consider submitting as a VPSP2 Regionally Driven Potential Project (Roadway Program). | WRC or VTrans (Planning) | Town of Wilmington, WRC, VTrans (Traffic Operations, Planning, Permitting and others) | Short Term (1-5 years) | Low ($0 - $100,000) |  | 24.803 | 25.555 | 2.821 | 3.573
3003 | Wilmington |  | Route 100N intersection and Beaver St | The Route 100 North intersection has various issues, including congestion and geometry issues. The proximity of the narrow bridge 31 (traffic width and stream width) adds complexity to the area. | Develop Roadway Master Plan for this section | Complete a Master Plan for downtown Wilmington that examines the issues and presents next steps. Consider submitting Bridge 31 and intersection as a VPSP2 Regionally Driven Potential Project (State Bridge, and Traffic and Safety Programs). | WRC or VTrans (Planning) | Town of Wilmington, WRC, VTrans (Traffic Operations, Planning, Permitting, AMB and others) | Short Term (1-5 years) | Low ($0 - $100,000) |  | 24.997 | -1 | 3.015 | -1
3058 | Wilmington |  | Merrill Dr to Hall Rd | Beaver Brook is "stressed" with problems of channel relocation, straightening, pollutants and sediment. Need to be careful to ensure waterway is not to be downgraded to "impaired". | Improve drainage and/or stormwater provisions | Monitor for water quality impacts | VTrans (Environmental, District) | ANR | Short Term (1-5 years) |  |  | 25.367 | 28.757 | 3.385 | 6.593
3067 | Wilmington |  | Rite Aid turn lane | Turn lane was installed near Rite Aid with short configuration. Appears to be working well. | No action needed | No action needed. | VTrans (District) |  | Short Term (1-5 years) |  |  | 25.541 | -1 | 3.55 | 0
3077 | Wilmington |  | Between White House Inn and Ballou Hill Road | Town are planning to construct a water and wastewater line extension | Coordinate about installation of new water and wastewater lines. | Unknown next steps | Town of Wilmington | VTrans (District, Permitting) | Short Term (1-5 years) |  |  | 25.831 | 26.54 | 3.849 | 0
3068 | Wilmington |  | Retaining walls near the White House Inn | Retaining walls are in poor condition and have issues with mowing and blowing snow. | Evaluate need for retaining walls and how to complete mowing | VTrans Geotechnical Section evaluate retaining walls to make recommendations. | VTrans (District, Geotechnical) |  | Short Term (1-5 years) |  |  | 25.861 | -1 | 3.879 | 0
3035 | Wilmington |  | Flea Market and White House Inn | Issues with blowing snow. | Improve snow removal ability | Evaluate winter maintenance and explore adding fencing to control blowing snow. | VTrans (District, Safety) |  | Short Term (1-5 years) |  |  | 25.94 | -1 | 3.958 | -1
3005 | Wilmington |  | Route 100S intersection | The Route 100 South intersection has congestion issues with intersection analysis showing Poor Level of Service (F) for 2020. Options to address the congestion include turn lanes, traffic signals and roundabouts. Intersection also has crash patterns that indicate some counter-measures. | Improve traffic flow | Evaluate which solutions are preferred to address the traffic and safety issues, potentially through a Scoping Study led by VTrans Traffic Design. Consider submitting as a VPSP2 Regionally Driven Potential Project (Traffic and Safety Program) | WRC or VTrans (Traffic Operations, Safety, Traffic Design) |  | Short Term (1-5 years) |  |  | 26.14 | -1 | 4.158 | -1
3046 | Wilmington |  | Near Shearer Hill Rd | Wood turtle can be found in this area so activity in this area should be careful. | Evaluate mowing practices and/or vegetation management | Coordinate with VTrans Environmental Section (Biologist) when work is done in this area. | VTrans (AMB, District, Environmental) | ANR | Short Term (1-5 years) |  |  | 27.046 | -1 | 5.064 | -1
3024 | Wilmington |  | Sparrow Lane | River is very exposed in this area. Could mowing practices be altered? | Evaluate mowing practices and/or vegetation management | Discuss maintenance and mowing practices to evaluate where practices may be altered | VTrans (District) | ANR | Short Term (1-5 years) | Low ($0 - $100,000) |  | 28.26 | -1 | 6.278 | -1
3006 | Wilmington |  | Molly Stark State Park | Emerging parking, snow removal and safety issues for people accessing Molly Stark State Park, particularly in the winter when people are parking on Route 9. | Improve safety near recreation area | Coordinate between stakeholders to look for solutions to the emerging parking, snow removal and safety issues. Evaluate need for signage warning about pedestrians in the roadway. Coordinate with 3002, 3072 and 3073? | WRC | ANR (Forest, Parks and Recreation), BCRC, WRC, VTrans (District, Traffic Operations, Planning) | Short Term (1-5 years) | Low ($0 - $100,000) |  | 28.324 | -1 | 6.342 | -1
3036 | Marlboro |  | West of Hogback Mountain | Frost heaves are common in this section, requiring some warning signs and also more pavement repairs | Improve drainage and/or stormwater provisions | Some improvements to be made through the 2021-2023 Paving Project, including installation of underdrain and drainage improvements. Monitor roadway after paving/reclaim project to see whether further improvements to drainage are needed (frost heave area) | VTrans (AMB) |  | Short Term (1-5 years) |  |  | 29.142 | 29.642 | 0 | 0.5
3015 | Marlboro |  | Between Old Hogback Rd and Sun and Ski Rd | Crashes occur here during icy conditions and when there is blowing snow. Explore safety improvements. | Improve roadway safety (section or intersection) | Evaluate winter maintenance and explore adding fencing to control blowing snow. | VTrans (District, Safety) |  | Short Term (1-5 years) |  |  | 29.242 | -1 | 0.1 | -1
3007 | Marlboro |  | Hogback Mountain | Safety concerns around the Hogback Mountain curve with numerous recorded crashes and near misses. Overlook on the curve contributes parking vehicles and pedestrians into the roadway. | Develop Roadway Master Plan for this section | Complete a Master Plan that examines issues and presents next steps. Consider studying drainage issues in 3037 in the same study. Consider submitting as a VPSP2 Regionally Driven Potential Project (Traffic and Safety Program). | WRC or VTrans (Planning) | Town of Marlboro, WRC, VTrans (Traffic Operations, Planning, Permitting, AMB and others), Local Businesses | Short Term (1-5 years) | Low ($0 - $100,000) |  | 29.742 | -1 | 0.6 | -1
3008 | Marlboro |  | Curve near Hughes Road | Curve near Hughes Road can be slippery due to blowing snow which causes crashes. | Improve roadway safety (section or intersection) | Programmed paving project due to address superelevation issue in 2021 and 2022 - NH 2971(1). Evaluate winter maintenance and explore adding fencing to control blowing snow. | VTrans (District, Safety) |  | Short Term (1-5 years) |  |  | 31.042 | -1 | 1.9 | -1
3037 | Marlboro |  | East of Hogback Mountain | Drainage issues here, particularly with natural springs nearby. Drainage improvements needed. | Improve drainage and/or stormwater provisions | Some improvements to be made through the 2021-2023 Paving Project, including installation of underdrain and drainage improvements. Monitor roadway after project to see if additional work is needed (coordinate with 3007 Hogback Mountain Master Plan?) | VTrans (Traffic Operations, Planning, Permitting and others) | Town of Marlboro, WRC | Short Term (1-5 years) |  |  | 31.042 | -1 | 0.8 | -1
3016 | Marlboro |  | Augur Hole Road | Augur Hole Road and other local roads are used as a cut through to Route 100, Dover and the ski areas during peak travel times. Local Towns (Marlboro and others) are concerned about traffic, speeding and increased maintenance burdens. In summer/ fall 2020 VTrans Staff were working on signage to help address the issue. | Evaluate signage and/or road markings | In fall 2020 VTrans Staff installed signage on state highways to help address the issue, as well as worked with the Towns with recommendations for their roadways. | VTrans (Joe Kelly is the lead) | Town of Marlboro, Town of Wilmington, WRC | Short Term (1-5 years) | Low ($0 - $100,000) |  | 32.859 | -1 | 3.717 | -1
3010 | Marlboro |  | South Road intersection | The South Road curve and intersection is an area of concern for safety. | Improve roadway safety (section or intersection) | Programmed paving project due to address some issues in this area, including installation of a left turn lane, in 2021 and 2022 - NH 2971(1) - https://resources.vtrans.vermont.gov/factsheet/default.aspx?pin=16V105. | VTrans Paving (Project Manager is Matthew Bogaczyk) |  | Short Term (1-5 years) |  |  | 34.592 | -1 | 5.45 | -1
3011 | Marlboro |  | Marlboro Elementary School | The roadway near the Marlboro Elementary School with the climbing lane has safety concerns. | Improve roadway safety (section or intersection) | Programmed paving project due to make improvements in 2021 and 2022 - NH 2971(1) - https://resources.vtrans.vermont.gov/factsheet/default.aspx?pin=16V105. Truck climbing lane options were evaluated. Partner with town to further improve sight distances. | VTrans Paving (Project Manager is Matthew Bogaczyk) | Town of Marlboro | Short Term (1-5 years) |  |  | 34.843 | -1 | 5.7 | 0
3023 | Marlboro |  | Climbing lane | Sinkholes are an intermittent issues on the climbing lane due to drainage issues. | Improve drainage and/or stormwater provisions | Monitor area and involve VTrans Geotechnical staff as needed. | VTrans (District, Geotechnical) |  | Short Term (1-5 years) |  |  | 36 | 37 | 6.862 | 7.862
3111 | Marlboro |  | West of MacArthur Road | Add signage to warn about blind driveways on curve | Evaluate signage and/or road markings | Evaluate whether a blind driveway sign is warranted. | VTrans (Traffic Operations) |  | Short Term (1-5 years) | Low ($0 - $100,000) |  | 36.388 | -1 | 7.246 | 0
3009 | Marlboro |  | Turners Corner | Turners Corner is a safety concern, particularly with the lack of sight distance near the Hamilton Road intersection. The 2021 paving project is working to address some of the issues (https://resources.vtrans.vermont.gov/factsheet/default.aspx?pin=20D120). | Improve roadway safety (section or intersection) | Programmed paving project due to address several issues in this area in 2021 and 2022 - NH 2971(1) - https://resources.vtrans.vermont.gov/factsheet/default.aspx?pin=16V105. Partner with Town to explore options for changing Hamilton Road access to VT 9. | VTrans Paving (Project Manager is Matthew Bogaczyk) | Town of Marlboro | Short Term (1-5 years) |  |  | 36.902 | -1 | 7.76 | -1
3039 | Marlboro | Brattleboro | Marlboro Collision | Section was lost in Tropical Storm Irene and is still at risk for future flooding and damage. Site is included within a FEMA Pre-Disaster Mitigation Project grant application. Project is being developed now with the construction hoped for 2022. | Improve roadway resilience | Pending environmental reviews, construction of mitigation efforts is due in 2022. | VTrans (Project Manager is Matt Bogaczyk) | Vermont Emergency Management | Short Term (1-5 years) | Medium ($100,000 - $1 million) | Pre-Disaster Mitigation Program (via VEM/ FEMA) | 37.192 | 37.666 | 8.05 | 0.22
3040 | Brattleboro |  | East of Stark Road | Section was damaged in Tropical Storm Irene and is still at risk for future flooding and damage. Site is included within a FEMA Pre-Disaster Mitigation Project grant application. Project is being developed now with the construction hoped for 2022. | Improve roadway resilience | Pending environmental reviews, construction of mitigation efforts is due in 2022. | VTrans (Project Manager is Matt Bogaczyk) | Vermont Emergency Management | Short Term (1-5 years) | Medium ($100,000 - $1 million) | Pre-Disaster Mitigation Program (via VEM/ FEMA) | 38.947 | -1 | 1.5 | -1
3041 | Brattleboro |  | Between Stark Road and Cook Rd | Section was severely impacted in Tropical Storm Irene and is still at risk for future flooding. Site is included within a FEMA Pre-Disaster Mitigation Project grant application. Project is being developed now with the construction hoped for 2022. | Improve roadway resilience | Pending environmental reviews, construction of mitigation efforts is due in 2022. | VTrans (Project Manager is Matt Bogaczyk) | Vermont Emergency Management | Short Term (1-5 years) | Medium ($100,000 - $1 million) | Pre-Disaster Mitigation Program (via VEM/ FEMA) | 39.296 | -1 | 1.85 | -1
3069 | Brattleboro |  | W. Brattleboro between Sunset Lake Rd and Edward H | Area has various issues, including many turning vehicles, lack of sidewalks and minimal lighting. Bike lanes and crosswalks are being installed in the upcoming paving project. | Develop Roadway Master Plan for this section | Develop Roadway Master Plan for this section, with drainage issues in 3017. Evaluating whether roadway should become Class 1 Town Highway in future may be useful. Consider submitting as a VPSP2 Regionally Driven Potential Project (Roadway Program). | WRC or VTrans (Planning) | Town of Brattleboro, WRC, VTrans (Traffic Operations, Planning, Permitting and others) | Short Term (1-5 years) | Low ($0 - $100,000) |  | 40.616 | 41.622 | 3.17 | 4.179
3113 | Brattleboro |  | Edward Height Road | Improve visibility of speed limit change sign. There are existing "Reduced Speed Limit Ahead" (W3-5) warning signs in place, in addition to upsized signs at the transition point. Could a radar speed feedback sign be added here? | Evaluate signage and/or road markings | Evaluate need for radar speed feedback sign and additional follow-up speed limit signs just beyond the speed limit changes. | Town of Brattleboro | WRC | Short Term (1-5 years) | Low ($0 - $100,000) |  | 40.616 | -1 | 3.17 | 0
3042 | Brattleboro |  | Chelsea Royal Diner | The road includes a section where a turning lane may be added in the future. | Turn lane being installed | Programmed paving project due to install two way left turn lane in this area in 2021 and 2022 - NH 2971(1) - https://resources.vtrans.vermont.gov/factsheet/default.aspx?pin=16V105. | VTrans (Project Manager is Matt Bogaczyk) |  | Short Term (1-5 years) |  |  | 40.731 | -1 | 3.285 | -1
3014 | Brattleboro |  | Bridge 51 near Westgate Drive | Bridge 51 has river alignment issues that exacerbate flooding issues. The bridge is a high risk according to the Vermont Transportation Resiliency Planning Tool. VTrans has applied for a Pre-Disaster Mitigation Project (Priority Site 4) to carry out mitigation efforts including restoring the flood chute and floodplain to improvement stream alignment and reduce bridge vulnerability, and repairing holes in the bridge abutment armor. The application was submitted in 2019 and, pending environmental reviews, construction is expected in 2022 | Improve how water travels through the bridge | Pending environmental reviews, construction of mitigation efforts is due in 2022. | VTrans (Project Manager is Matt Bogaczyk) | Vermont Emergency Management | Short Term (1-5 years) | Medium ($100,000 - $1 million) | Pre-Disaster Mitigation Program (via VEM/ FEMA) | 40.897 | -1 | 3.45 | -1
3012 | Brattleboro |  | Bridge 54 near Melrose St | Bridge 54 on Western Ave is a local concern for bicycle and pedestrian issues. It is narrow and there is little space for bicyclists when large trucks are sharing the bridge. | Improve bicycle and pedestrian safety on bridge | Consider needs of bicyclists and pedestrians when construction project is project for the bridge or nearby. Town Highway Bridge is currently in scoping (BRATTLEBORO BF 2000(28)) | VTrans Structures (Project Manager is Laura Stone) | Town of Brattleboro | Short Term (1-5 years) |  |  | 42.525 | -1 | 5.079 | -1
3059 | Brattleboro |  | East of Brattleboro Farmers Market | Whetstone Brook is "impaired" meaning there are strick EPA regulations in this area. | Improve drainage and/or stormwater provisions | Monitor for water quality impacts | VTrans (Environmental, District) | ANR | Short Term (1-5 years) |  |  | 43.116 | -1 | 5.67 | 0
3114 | Bennington | All towns | Corridor wide | Consider noise generation of paving surfaces used on the roadway. | Investigate noise generation of paving surfaces | Consider noise generation of paving surfaces when doing paving projects. Consider a statewise research project looking at noise generation if one has not been done recently. | VTrans (Project Delivery Bureau, Research Bureau) |  | Medium Term (5-10 years) |  |  | 5.8 | 43.297 | 5.8 | 5.851
3117 | Bennington | All towns | Corridor wide | Consider narrow shoulders and bicycle traffic when installing rumble stripes along the Corridor. Centerline rumble stripes can make drivers reluctant to move over for bicyclists | Consider bicyclists when installing rumble stripes | Rumble Stripe Policy is not due for revision at this time so action is necessary. | VTrans (Safety) |  | Medium Term (5-10 years) |  |  | 5.8 | 43.297 | 5.8 | 5.851
3108 | Bennington |  | Bridge 9 | Monitor bridge which is a high risk from the resliency perspective according to the Transportation Resiliency Planning Tool. | Monitor area of high risk for resiliency | Monitor roadway section and prioritize resiliency efforts through the Part 667 Process. | VTrans (District, AMB) | Vermont Emergency Management | Medium Term (5-10 years) |  |  | 6.4 | -1 | 6.4 | 0
3029 | Woodford |  | East of Harbor Road | The river jumps its banks here and has the potential to cause roadway impacts. | Monitor river/ stream for flooding and movement | Monitor roadway and consider future mitigation project. | VTrans (District) |  | Medium Term (5-10 years) |  |  | 8.57 | -1 | 1.701 | -1
3062 | Woodford |  | East of the Woodford notch | The river regularly jumps its banks here causing roadway impacts. | Improve roadway resilience | Monitor roadway section and prioritize resiliency efforts through the Part 667 Process. | VTrans (District, AMB) | Vermont Emergency Management | Medium Term (5-10 years) |  |  | 9.117 | -1 | 2.25 | -1
3098 | Wilmington |  | Primrose Lane/Oxbow Loop to Route 100N | Monitor roadway section which is a high risk from the resiliency perspective according to the Transportation Resiliency Planning Tool. | Improve roadway resilience | Monitor roadway section and prioritize resiliency efforts through the Part 667 Process. | VTrans (District, AMB) | Vermont Emergency Management | Medium Term (5-10 years) |  |  | 23.071 | 24.997 | 1.088 | 3.015
3106 | Wilmington |  | Bridge 30 | Monitor bridge which is a high risk from the resliency perspective according to the Transportation Resiliency Planning Tool. | Monitor area of high risk for resiliency | Monitor roadway section and prioritize resiliency efforts through the Part 667 Process. | VTrans (District, AMB) | Vermont Emergency Management | Medium Term (5-10 years) |  |  | 24.181 | -1 | 2.2 | 0
3033 | Wilmington |  | Wilmington Inn | Roadway section destabilized next to the river requiring two fixes. The area now appears to be stabilized. | Improve roadway resilience | Monitor roadway section and prioritize resiliency efforts through the Part 667 Process. | VTrans (District, AMB) | Vermont Emergency Management | Medium Term (5-10 years) |  |  | 24.75 | -1 | 2.768 | -1
3099 | Wilmington |  | Sherer Hill Rd to Molly Stark State Park | Monitor roadway section which is a high risk from the resiliency perspective according to the Transportation Resiliency Planning Tool. | Improve roadway resilience | Monitor roadway section and prioritize resiliency efforts through the Part 667 Process. | VTrans (District, AMB) | Vermont Emergency Management | Medium Term (5-10 years) |  |  | 27.065 | 28.323 | 5.083 | 6.341
3048 | Wilmington |  | Between Shearer Hill Rd and Cornell Way | Land between river and road should be monitored as additional riprap may be needed in the future. | Improve roadway resilience | Monitor roadway section and prioritize resiliency efforts through the Part 667 Process. | VTrans (District, AMB) | Vermont Emergency Management, ANR | Medium Term (5-10 years) |  |  | 27.481 | -1 | 5.499 | -1
3100 | Marlboro | Brattleboro | Hamilton Rd (west end) to Cider Mill Hill | Monitor roadway section which is a high risk from the resiliency perspective according to the Transportation Resiliency Planning Tool. | Improve roadway resilience | Monitor roadway section and prioritize resiliency efforts through the Part 667 Process. | VTrans (District, AMB) | Vermont Emergency Management | Medium Term (5-10 years) |  |  | 36.962 | 39.549 | 7.82 | 2.103
3057 | Marlboro | Brattleboro | Marlboro Collision to Stark Rd | Roadway is vulnerable with its proximity to the stream and should be monitored. | Improve roadway resiliency | Monitor roadway section and prioritize resiliency efforts if necessary. | VTrans (District) | Vermont Emergency Management, ANR | Medium Term (5-10 years) |  |  | 37.043 | 38.54 | 7.901 | 1.094
3065 | Marlboro |  | East of eastern end of Hamilton Rd | Snow removal is challenging in this area because the ledge is very close to the roadway so there is no space for snow storage. Section assessed by VTrans Geotechnical Staff but has no simple fixes so would need detailed geotechnical evaluation before pursuing further options. | Improve snow removal ability | Complete detailed geotechnical evaluation to determine appropriate treatment options to address needs. | VTrans (AMB, Geotechnical) |  | Medium Term (5-10 years) |  |  | 38.466 | -1 | 1.02 | -1
3078 | Brattleboro |  | Class 1 Town Highway (Edward Heights - I-91) | Old concrete roadbed is causing issues for maintenance of the Class 1 Town Highway. Concrete slab removal would be town responsibility, although could work with VTrans to coordinate with upcoming Class 1 Paving Project (Town would have to find independent funding). | Explore options to reduce negative impacts of old concrete roadbed | Town develop a plan to address needs including non-VTrans funds. Potentially consider coordination of various projects with the next Class 1 TH paving project that is due around 2029. | Town of Brattleboro | VTrans (PDB), WRC | Medium Term (5-10 years) |  |  | 40.616 | 43.297 | 3.17 | 5.851
3017 | Brattleboro |  | West Brattleboro Dunkin Donuts | The area has severe drainage issues, particularly in the winter and spring. Water bubbles up and ice forms, up to a foot thick in places. The issue begins with a stormwater drainage pond on private property, but is also affected by issues from driveways and local drainage for approximately 1,000 ft of roadway. | Develop Roadway Master Plan for this section | Develop Roadway Master Plan for this section to look at drainage and access management issues. When considering solution, evaluate alongside issues in 3069 Consider submitting as a VPSP2 Regionally Driven Potential Project (Roadway Program). | WRC or VTrans (Planning) | Town of Brattleboro, WRC, VTrans (Traffic Operations, Planning, Permitting and others) | Medium Term (5-10 years) |  |  | 41.045 | -1 | 3.599 | 0
3105 | Brattleboro |  | Meadowbrook Rd to Guilford St | Monitor roadway section which is a high risk from the resiliency perspective according to the Transportation Resiliency Planning Tool. | Improve roadway resilience | Monitor roadway section and prioritize resiliency efforts through the Part 667 Process. | VTrans (District, AMB) | Vermont Emergency Management | Medium Term (5-10 years) |  |  | 41.907 | 43.024 | 4.461 | 5.578
3107 | Brattleboro |  | Bridge 52 | Monitor bridge which is a high risk from the resliency perspective according to the Transportation Resiliency Planning Tool. | Monitor area of high risk for resiliency | Monitor roadway section and prioritize resiliency efforts through the Part 667 Process. | VTrans (District, AMB) | Vermont Emergency Management | Medium Term (5-10 years) |  |  | 41.916 | -1 | 4.47 | 0
3070 | Brattleboro |  | W. Brattleboro between Greenleaf St and Melrose St | Area has several issues converging including drainage, safety, bicycle and pedestrian, and pavement condition. Refer to the 2014 West Brattleboro Bicycle and Pedestrian Scoping Study for more information and alternatives. | Improve drainage, safety and pavement condition | Town develop a plan to address needs including non-VTrans funds. Potentially consider coordination of various projects with the next Class 1 TH paving project that is due around 2029. | Town of Brattleboro | VTrans (PDB), WRC | Medium Term (5-10 years) |  |  | 42.031 | 42.549 | 4.585 | 5.102
3122 | Brattleboro |  | Guilford Road intersection | Traffic backs up past exit 2 when someone is trying to turn onto Guilford Street going westbound on Route 9. Improve traffic flow at the Guilford Street intersection. | Improve traffic flow | Town develop a plan to address needs. Potentially consider coordination of various projects with the next Class 1 TH paving project that is due around 2029. | Town of Brattleboro | WRC | Medium Term (5-10 years) |  |  | 43.024 | -1 | 5.578 | 0
3021 | Searsburg |  | Lind Lane loop | The river near Lind Lane is very active and while the bridges are a good size, they may be at risk if the river changes its channel. | Monitor river/ stream for flooding and movement | Monitor movement of the river channel. If major changes occur the existing bridge sizes may become insufficient. |  |  | Long Term (>10 but active) |  |  | 20.567 | 20.944 | 4.123 | 4.5
3101 | Bennington | All towns | Corridor wide | Inconsistent and sometimes narrow shoulders can cause issues for maintenance and travel. | Increase roadway width | Consider increasing shoulder widths along the roadway in future paving projects with appropriate scope (eg reclaim rather than leveling). These improvements are included in the 2021/2022 Paving project from Wilmington to Brattleboro (NH 2971(1)). | VTrans (AMB) |  | Await harmonization opportunity |  |  | 5.8 | 43.297 | 5.8 | 5.851
3103 | Bennington | All towns | Corridor wide | The land adjacent to Route 9 is part of an important wildlife habitat and travel corridor. Wildlife crossings should be considered with structure upgrades and education of the traveling public may be good to consider. | Consider accommodating wildlife when rehabilitating or replacing structure | Coordinate with VTrans Environmental Section (Biologist) when work is done in this area. Evaluate need for wildlife crossing area and feasibility of upgrading structures when harmonization opportunity arises. | VTrans (AMB, Structures, Environmental) | ANR | Await harmonization opportunity |  |  | 5.8 | 43.297 | 5.8 | 5.851
3123 | Bennington | All towns | Corridor wide | Many cars pass on the right in the parking/ emergency lane, particularly when people are trying to make a left turn into a driveway or a road | Education about passing on the right | Per state statute vehicles may overtake on the right if the vehicle being overtaken is making a left turn. As such, no action is recommended for corridor, except to evaluate safety at intersections when projects arise. | VTrans (Traffic Operations, Project Delivery Bureau) | Governor's Highway Safety Alliance | Await harmonization opportunity |  |  | 5.8 | 43.297 | 5.8 | 5.851
3129 | Bennington | All towns | Corridor wide | Evaluate transit connections and facilities along the corridor, particularly opportunities to improve connections between transit routes and providing safe places for people to wait for the bus where there is not a sidewalk. | Improve transit | When transit planning study or route changes are next proposed for the area, consider opportunities to improve service (including connections) and locations where bus stop facilities and safety could be improved. | SEVT, GMCN, VTrans (Public Transit) | Southeast Vermont Transit, Green Mountain Community Network, Towns | Await harmonization opportunity |  |  | 5.8 | 43.297 | 5.8 | 5.851
3060 | Woodford |  |  | Culvert is insufficient for aquatic organism passage. | Consider accommodating wildlife when rehabilitating or replacing structure | Coordinate with VTrans Environmental Section (Biologist) when work is done in this area. Evaluate need for wildlife crossing area and feasibility of upgrading structures when harmonization opportunity arises. | VTrans (AMB, Structures, Environmental) | ANR | Await harmonization opportunity |  |  | 7.031 | -1 | 0.162 | -1
3061 | Woodford |  |  | Culvert is insufficient for aquatic organism passage. | Consider accommodating wildlife when rehabilitating or replacing structure | Coordinate with VTrans Environmental Section (Biologist) when work is done in this area. Evaluate need for wildlife crossing area and feasibility of upgrading structures when harmonization opportunity arises. | VTrans (AMB, Structures, Environmental) | ANR | Await harmonization opportunity |  |  | 7.371 | -1 | 0.502 | -1
3080 | Woodford |  |  | Wildlife crossing area (bears) | Consider accommodating wildlife when rehabilitating or replacing structure | Coordinate with VTrans Environmental Section (Biologist) when work is done in this area. Evaluate need for wildlife crossing area and feasibility of upgrading structures when harmonization opportunity arises. | VTrans (AMB, Structures, Environmental) | ANR | Await harmonization opportunity |  |  | 10.821 | -1 | 3.952 | 0
3081 | Woodford |  |  | Wildlife crossing area (bears) | Consider accommodating wildlife when rehabilitating or replacing structure | Coordinate with VTrans Environmental Section (Biologist) when work is done in this area. Evaluate need for wildlife crossing area and feasibility of upgrading structures when harmonization opportunity arises. | VTrans (AMB, Structures, Environmental) | ANR | Await harmonization opportunity |  |  | 11.557 | -1 | 4.687 | 0
3071 | Woodford |  | Near entrance to Prospect Mountain | A study was completed in the past to evaluate extending the passing lane beyond the prospect Mountain entrance | Consider turn lane in future | Consider the study when a project arises in the future where there may be a harmonization opportunity. | VTrans (AMB) |  | Await harmonization opportunity |  |  | 11.722 | -1 | 4.853 | 0
3082 | Woodford |  |  | Wildlife crossing area (bears) | Consider accommodating wildlife when rehabilitating or replacing structure | Coordinate with VTrans Environmental Section (Biologist) when work is done in this area. Evaluate need for wildlife crossing area and feasibility of upgrading structures when harmonization opportunity arises.. | VTrans (AMB, Structures, Environmental) | ANR | Await harmonization opportunity |  |  | 12.1935 | -1 | 5.3245 | 0
3030 | Woodford |  | West of Woodford State Park | Roadway is narrow which particularly causes issues during winter weather when plows are out. | Increase roadway width | Explore expanding roadway width as part of future paving project where scope is sufficient (eg reclaim rather than leveling project). | VTrans (AMB, PDB) |  | Await harmonization opportunity |  |  | 13.953 | 14.712 | 7.084 | 7.843
3063 | Woodford |  | East of Woodford State Park | Roadway condition indicates that reconstruction is needed. | Reconstruct roadway in poor condition | Await road condition to be flagged through VTrans Asset Management Systems. | VTrans (AMB) |  | Await harmonization opportunity |  |  | 14.06 | 14.96 | 7.2 | 8.1
3083 | Woodford |  |  | Wildlife crossing area | Improve provisions for wildlife crossing | Coordinate with VTrans Environmental Section (Biologist) when work is done in this area. Evaluate need for wildlife crossing area and feasibility of upgrading structures when harmonization opportunity arises. | VTrans (AMB, Structures, Environmental) | ANR | Await harmonization opportunity |  |  | 14.395 | -1 | 7.526
3056 | Woodford |  | State Park Road | Culvert is an important wetland crossing that needs improvements for aquatic organism passage. | Consider accommodating wildlife when rehabilitating or replacing structure | Coordinate with VTrans Environmental Section (Biologist) when work is done in this area. Evaluate need for wildlife crossing area and feasibility of upgrading structures when harmonization opportunity arises. | VTrans (AMB, Structures, Environmental) | ANR | Await harmonization opportunity |  |  | 14.705 | -1 | 7.836 | -1
3084 | Woodford |  |  | Wildlife crossing area (bears) | Consider accommodating wildlife when rehabilitating or replacing structure | Coordinate with VTrans Environmental Section (Biologist) when work is done in this area. Evaluate need for wildlife crossing area and feasibility of upgrading structures when harmonization opportunity arises. | VTrans (AMB, Structures, Environmental) | ANR | Await harmonization opportunity |  |  | 14.755 | -1 | 7.886
3055 | Woodford |  | Red Mill Pond outlet | Culvert is undersized, perched and impassable for aquatic organism passage. | Consider accommodating wildlife when rehabilitating or replacing structure | Coordinate with VTrans Environmental Section (Biologist) when work is done in this area. Evaluate need for wildlife crossing area and feasibility of upgrading structures when harmonization opportunity arises. | VTrans (AMB, Structures, Environmental) | ANR | Await harmonization opportunity |  |  | 15.48 | -1 | 8.611 | -1
3085 | Woodford |  |  | Wildlife crossing area (bears) | Consider accommodating wildlife when rehabilitating or replacing structure | Coordinate with VTrans Environmental Section (Biologist) when work is done in this area. Evaluate need for wildlife crossing area and feasibility of upgrading structures when harmonization opportunity arises. | VTrans (AMB, Structures, Environmental) | ANR | Await harmonization opportunity |  |  | 15.739 | -1 | 8.87
3054 | Woodford |  | East of Red Mill Campground Rd | Culvert is an important wetland crossing that only has partial aquatic organism passage. | Consider accommodating wildlife when rehabilitating or replacing structure | Coordinate with VTrans Environmental Section (Biologist) when work is done in this area. Evaluate need for wildlife crossing area and feasibility of upgrading structures when harmonization opportunity arises. | VTrans (AMB, Structures, Environmental) | ANR | Await harmonization opportunity |  |  | 15.863 | -1 | 8.994 | -1
3086 | Woodford |  |  | Wildlife crossing area | Consider accommodating wildlife when rehabilitating or replacing structure | Coordinate with VTrans Environmental Section (Biologist) when work is done in this area. Evaluate need for wildlife crossing area and feasibility of upgrading structures when harmonization opportunity arises. | VTrans (AMB, Structures, Environmental) | ANR | Await harmonization opportunity |  |  | 16.07 | -1 | 9.2
3087 | Woodford | Searsburg |  | Wildlife crossing area (bears) | Consider accommodating wildlife when rehabilitating or replacing structure | Coordinate with VTrans Environmental Section (Biologist) when work is done in this area. Evaluate need for wildlife crossing area and feasibility of upgrading structures when harmonization opportunity arises. | VTrans (AMB, Structures, Environmental) | ANR | Await harmonization opportunity |  |  | 16.207 | 17.212 | 9.338 | 0.768
3088 | Searsburg |  |  | Wildlife crossing area (bears) | Consider accommodating wildlife when rehabilitating or replacing structure | Coordinate with VTrans Environmental Section (Biologist) when work is done in this area. Evaluate need for wildlife crossing area and feasibility of upgrading structures when harmonization opportunity arises. | VTrans (AMB, Structures, Environmental) | ANR | Await harmonization opportunity |  |  | 17.561 | -1 | 1.117
3089 | Searsburg |  |  | Wildlife crossing area | Consider accommodating wildlife when rehabilitating or replacing structure | Coordinate with VTrans Environmental Section (Biologist) when work is done in this area. Evaluate need for wildlife crossing area and feasibility of upgrading structures when harmonization opportunity arises. | VTrans (AMB, Structures, Environmental) | ANR | Await harmonization opportunity |  |  | 17.61 | -1 | 1.166
3090 | Searsburg |  |  | Wildlife crossing area | Consider accommodating wildlife when rehabilitating or replacing structure | Coordinate with VTrans Environmental Section (Biologist) when work is done in this area. Evaluate need for wildlife crossing area and feasibility of upgrading structures when harmonization opportunity arises. | VTrans (AMB, Structures, Environmental) | ANR | Await harmonization opportunity |  |  | 17.832 | -1 | 1.388
3091 | Searsburg |  |  | Wildlife crossing area | Consider accommodating wildlife when rehabilitating or replacing structure | Coordinate with VTrans Environmental Section (Biologist) when work is done in this area. Evaluate need for wildlife crossing area and feasibility of upgrading structures when harmonization opportunity arises. | VTrans (AMB, Structures, Environmental) | ANR | Await harmonization opportunity |  |  | 18.093 | -1 | 1.649
3052 | Searsburg |  | Near Route 8 intersection | Bridge is undersized and has reduced aquatic organism passage. | Consider accommodating wildlife when rehabilitating or replacing structure | Coordinate with VTrans Environmental Section (Biologist) when work is done in this area. Evaluate need for wildlife crossing area and feasibility of upgrading structures when harmonization opportunity arises. | VTrans (AMB, Structures, Environmental) | ANR | Await harmonization opportunity |  |  | 18.149 | -1 | 1.705 | 0
3053 | Searsburg |  | Near Town Line Road | Culvert is perched and is an important wetland crossing without good aquatic organism passage. | Consider accommodating wildlife when rehabilitating or replacing structure | Coordinate with VTrans Environmental Section (Biologist) when work is done in this area. Evaluate need for wildlife crossing area and feasibility of upgrading structures when harmonization opportunity arises. | VTrans (AMB, Structures, Environmental) | ANR | Await harmonization opportunity |  |  | 18.149 | -1 | 0.068 | 0
3092 | Searsburg |  |  | Wildlife crossing area (bears) | Consider accommodating wildlife when rehabilitating or replacing structure | Coordinate with VTrans Environmental Section (Biologist) when work is done in this area. Evaluate need for wildlife crossing area and feasibility of upgrading structures when harmonization opportunity arises. | VTrans (AMB, Structures, Environmental) | ANR | Await harmonization opportunity |  |  | 18.338 | 19.645 | 1.894 | 3.201
3032 | Searsburg |  | East of top escape ramp | Guardrail damage and crash pattern identified by VTrans staff with next steps suggested - superelevation evaluation, winter maintenance evaluation, ITS warnings, potential high friction surface treatment candidate. | Improve roadway safety (section or intersection) | Evaluate roadway banking and incorporate improvements into future paving project with appropriate scope (eg reclaim rather than leveling) | VTrans (District, AMB) |  | Await harmonization opportunity |  |  | 19.088 | -1 | 2.644 | 0
3093 | Searsburg |  |  | Wildlife crossing area (bears) | Consider accommodating wildlife when rehabilitating or replacing structure | Coordinate with VTrans Environmental Section (Biologist) when work is done in this area. Evaluate need for wildlife crossing area and feasibility of upgrading structures when harmonization opportunity arises. | VTrans (AMB, Structures, Environmental) | ANR | Await harmonization opportunity |  |  | 20.2 | -1 | 3.756
3051 | Searsburg |  | Near Woods Road in Medbury | Culvert is undersized and has reduced aquatic organism passage. | Consider accommodating wildlife when rehabilitating or replacing structure | Coordinate with VTrans Environmental Section (Biologist) when work is done in this area. Evaluate need for wildlife crossing area and feasibility of upgrading structures when harmonization opportunity arises. | VTrans (AMB, Structures, Environmental) | ANR | Await harmonization opportunity |  |  | 22.087 | -1 | 0.105 | -1
3094 | Wilmington |  |  | Wildlife crossing area (bears) | Consider accommodating wildlife when rehabilitating or replacing structure | Coordinate with VTrans Environmental Section (Biologist) when work is done in this area. Evaluate need for wildlife crossing area and feasibility of upgrading structures when harmonization opportunity arises. | VTrans (AMB, Structures, Environmental) | ANR | Await harmonization opportunity |  |  | 22.678 | -1 | 0.696
3074 | Wilmington |  | West of Haystack road | The roadway is narrow between guardrails causing issues for oversized loads. The location of guardrails is partially constrained by the length of a box culvert and the proximity to Harriman Reservor. | Increase roadway width | Consider lengthening the box culvert, increasing shoulder widths and moving back guardrails in future projectes with appropriate scope. | VTrans (AMB) |  | Await harmonization opportunity |  |  | 23.714 | -1 | 1.732 | 0
3116 | Wilmington |  | Haystack Road intersection | Consider turn lane for Haystack Road intersection | Improve intersection | Evaluate need for turn lane at intersection when preparing for a future construction project. | VTrans (Traffic Operations/ Mobility) |  | Await harmonization opportunity |  |  | 23.887 | -1 | 1.905 | 0
3049 | Wilmington |  | Wilmington Inn and Tavern | Bridge is undersized, perched and insufficient for aquatic organism passage. | Consider accommodating wildlife when rehabilitating or replacing structure | Coordinate with VTrans Environmental Section (Biologist) when work is done in this area. Evaluate need for wildlife crossing area and feasibility of upgrading structures when harmonization opportunity arises. | VTrans (AMB, Structures, Environmental) | ANR | Await harmonization opportunity |  |  | 24.495 | -1 | 2.513 | -1
3050 | Wilmington |  | West Wilmington | Bridge is undersized, perched and insufficient for aquatic organism passage. | Consider accommodating wildlife when rehabilitating or replacing structure | Coordinate with VTrans Environmental Section (Biologist) when work is done in this area. Evaluate need for wildlife crossing area and feasibility of upgrading structures when harmonization opportunity arises. | VTrans (AMB, Structures, Environmental) | ANR | Await harmonization opportunity |  |  | 24.495 | -1 | 2.513 | 0
3076 | Wilmington |  | Near 1836 Country Store | Drainage issues in this area | Improve drainage and/or stormwater provisions | Consider incorporating drainage improvements into future paving project with appropriate scope (eg reclaim rather than leveling) | VTrans (AMB) |  | Await harmonization opportunity |  |  | 24.868 | -1 | 2.886 | 0
3075 | Wilmington |  | Beaver St intersection | Drainage issues near this intersection | Improve drainage and/or stormwater provisions | Consider incorporating drainage improvements into future paving project with appropriate scope (eg reclaim rather than leveling) | VTrans (AMB) |  | Await harmonization opportunity |  |  | 25.114 | -1 | 3.132 | 0
3004 | Wilmington |  | Shaws Plaza | The Shaws Plaza is an important part of the local transit network. Coordination with Transit companies is important when work is done in this area. | Consider transit needs in this area | Coordinate with transit companies when work is done in this area. |  |  | Await harmonization opportunity |  |  | 25.461 | -1 | 3.479 | -1
3047 | Wilmington |  | Wahoo's Eatery | Bridge is undersized and has reduced aquatic organism passage. | Consider accommodating wildlife when rehabilitating or replacing structure | Coordinate with VTrans Environmental Section (Biologist) when work is done in this area. Evaluate need for wildlife crossing area and feasibility of upgrading structures when harmonization opportunity arises. | VTrans (AMB, Structures, Environmental) | ANR | Await harmonization opportunity |  |  | 25.616 | -1 | 3.634 | -1
3097 | Wilmington |  | Sparrow Lane near Molly Stark State Park | Culvert is perched. | Remove perch when replacing culvert | Evaluate water quality issues and feasibility of upgrading structures when harmonization opportunity arises. | VTrans (AMB, Structures, Environmental) | ANR | Await harmonization opportunity |  |  | 28.215 | -1 | 6.233 | 0
3045 | Wilmington |  | Near Molly Stark State Park | Culvert is perched and insufficient for aquatic organism passage. | Consider accommodating wildlife when rehabilitating or replacing structure | Coordinate with VTrans Environmental Section (Biologist) when work is done in this area. Evaluate need for wildlife crossing area and feasibility of upgrading structures when harmonization opportunity arises. | VTrans (AMB, Structures, Environmental) | ANR | Await harmonization opportunity |  |  | 28.302 | -1 | 6.32 | -1
3119 | Wilmington |  | Near Molly Stark State Park | Consider wildlife crossing area near Molly Stark State Park where there is conserved land on both sides of the road. | Consider accommodating wildlife when rehabilitating or replacing structure | Evaluate need for wildlife crossing area and feasibility of upgrading structures when harmonization opportunity arises. | VTrans (AMB, Structures, Environmental) |  | Await harmonization opportunity |  |  | 28.381 | -1 | 6.399 | 0
3118 | Marlboro |  | Near Hogback Mountain | Consider wildlife crossing area near Hogback Mountain where there is conserved land on both sides of the road. | Consider accommodating wildlife when rehabilitating or replacing structure | Evaluate need for wildlife crossing area and feasibility of upgrading structures when harmonization opportunity arises. | VTrans (AMB, Structures, Environmental) |  | Await harmonization opportunity |  |  | 29.179 | -1 | 0.037 | 0
3025 | Marlboro |  |  | The culvert is important for terrestrial and amphibian crossing. | Consider accommodating wildlife when rehabilitating or replacing structure | Coordinate with VTrans Environmental Section (Biologist) when work is done in this area. Evaluate need for wildlife crossing area and feasibility of upgrading structures when harmonization opportunity arises. | VTrans (AMB, Structures, Environmental) | ANR | Await harmonization opportunity |  |  | 31.45 | -1 | 2.31 | -1
3026 | Marlboro |  |  | The culvert is important for terrestrial and amphibian crossing. | Consider accommodating wildlife when rehabilitating or replacing structure | Coordinate with VTrans Environmental Section (Biologist) when work is done in this area. Evaluate need for wildlife crossing area and feasibility of upgrading structures when harmonization opportunity arises. | VTrans (AMB, Structures, Environmental) | ANR | Await harmonization opportunity |  |  | 32.74 | -1 | 3.6 | -1
3027 | Marlboro |  |  | The culvert is important for terrestrial and amphibian crossing. | Consider accommodating wildlife when rehabilitating or replacing structure | Coordinate with VTrans Environmental Section (Biologist) when work is done in this area. Evaluate need for wildlife crossing area and feasibility of upgrading structures when harmonization opportunity arises. | VTrans (AMB, Structures, Environmental) | ANR | Await harmonization opportunity |  |  | 33.79 | -1 | 4.65 | -1
3038 | Marlboro |  | Between Church Hollow Rd and South Rd | Roadway is narrow and has bad drainage that needs attention. | Improve drainage and widen roadway | Consider incorporating drainage and shoulder improvements into future paving project with appropriate scope (eg reclaim rather than leveling). | VTrans (AMB) |  | Await harmonization opportunity |  |  | 33.992 | 34.542 | 4.85 | 5.4
3044 | Marlboro |  | Staver Road | Culvert is undersized and insufficient for aquatic organism passage. | Consider accommodating wildlife when rehabilitating or replacing structure | Coordinate with VTrans Environmental Section (Biologist) when work is done in this area. Evaluate need for wildlife crossing area and feasibility of upgrading structures when harmonization opportunity arises. | VTrrans (AMB, Structures, Environmental) | ANR | Await harmonization opportunity |  |  | 35.158 | -1 | 6.016 | -1
3028 | Marlboro |  |  | The culvert is important for terrestrial and amphibian crossing, including large mammals. | Consider accommodating wildlife when rehabilitating or replacing structure | Coordinate with VTrans Environmental Section (Biologist) when work is done in this area. Evaluate need for wildlife crossing area and feasibility of upgrading structures when harmonization opportunity arises. | VTrans (AMB, Structures, Environmental) | ANR | Await harmonization opportunity |  |  | 35.691 | -1 | 6.549 | -1
3127 | Marlboro |  | Near North Pond Road | Climbing lane merge occurs just before a sharp right which is challenging for drivers. | Evaluate climbing lane | When a project next goes through this area of appropriate scope, evaluate the location of the climbing lane merge (particularly given the sharp right turn). | VTrans (Traffic Operations, Project Delivery Bureau) |  | Await harmonization opportunity |  |  | 36.042 | -1 | 6.9 | 0
3128 | Marlboro |  | East of Augur Hole Road | The length of the climbing lane has been increasing which is causing issues for turning vehicles. | Evaluate climbing lane | When a project next goes through this area of appropriate scope, evaluate the location of the climbing lane merge (particularly given the sharp right turn). | VTrans (Traffic Operations, Project Delivery Bureau) |  | Await harmonization opportunity |  |  | 36.042 | -1 | 6.9 | 0
3066 | Brattleboro |  | West of McKays Auto | Winter thaw regularly creates standing water issues for property owners, an issue that also sometimes impacts the roadway. | Improve drainage and/or stormwater provisions | Consider incorporating drainage and other improvements into future paving project with appropriate scope (eg reclaim rather than leveling). | VTrans (AMB) |  | Await harmonization opportunity |  |  | 39.146 | -1 | 1.7 | 0
3018 | Brattleboro |  | Between Stockwell Dr and I-91 | Local transit buses find it hard to pull over and deploy their ramp for wheelchair passengers because the shoulder is narrow. | Consider transit needs in this area | Coordinate with transit companies when work is done in this area. |  |  | Await harmonization opportunity |  |  | 41.79 | 43.296 | 4.344 | 5.85
3022 | Brattleboro |  | East of Brattleboro Farmers Market | The Whetstone Brook east of the Brattleboro Farmers market is "impaired" so attention should be paid to stormwater in this area. | Improve drainage and/or stormwater provisions | Consider stormwater improvements in this area to improve water quality. | Town of Brattleboro | ANR | Await harmonization opportunity |  |  | 42.887 | 43.322 | 5.441 | 5.876
3019 | Brattleboro |  | I-91 Exit 2 | The idea of a Park and Ride Lot near Exit 2 has been discussed. If the ideas is further explored, coordination with the local transit provider, Southeast Vermont Transit, is important. | Consider transit needs in this area | Coordinate with transit companies when work is done in this area. |  |  | Await harmonization opportunity |  |  | 43.241 | -1 | 5.795 | 0
3104 | Bennington | All towns | Corridor wide | Underdrain has been installed in various places along the entire Corridor, but a plan for maintenance is needed for the long term effectiveness of this infrastructure | Improve drainage and/or stormwater provisions | Unknown next steps. Underdrain is currently only mapped and inspected by VTrans when associated with a regulated stormwater treatment system. | Unknown |  |  |  |  | 5.8 | 43.297 | 5.8 | 5.851
3124 | Bennington | All towns | Corridor wide | Speeding is an issue along the corridor. Evaluate reducing speed limit for the entire corridor to 45mph. Could automated speed enforcement also be considered for this corridor? | Evaluate speed limit | Due to state policy, the speed limit cannot be reduced to a blanket 45mph. Towns Requests for specific locations can be considered by the Traffic Committee. Automated speed enforcement is not currently allowed in Vermont per statute. | No action proposed |  |  |  |  | 5.8 | 43.297 | 5.8 | 5.851
3130 | Bennington | All towns | Corridor wide | Explore adding signage and markings related to bicyclists on the roadway - eg sharrows and Share the Road signs. | Evaluate signage and/or road markings | VTrans no longer supports the use of "Share the Road" signs and sharrows may only be used on roads with posted speed of 35 or less. Therefore no action is suggested. | No action proposed |  |  |  |  | 5.8 | 43.297 | 5.8 | 5.851
3034 | Wilmington |  | East of Haystack Rd | Underground spring causes issues for local property owners and is close to Route 9. | Improve drainage and/or stormwater provisions | Unknown next steps | Unknown |  |  |  |  | 23.998 | -1 | 2.016 | -1
3064 | Marlboro |  | East of Adams Crossroad | Snow removal is challenging in this area because the ledge is very close to the roadway on both sides so there is no space for snow storage. Section assessed by VTrans Geotechnical Staff and is not a priority from a rockfall perspective. | Improve snow removal ability | Unknown next steps | VTrans (AMB, Geotechnical) |  |  |  |  | 31.916 | -1 | 2.77 | -1
3125 | Brattleboro |  | West of Chelsea Royal Diner | When heading west there is a “Watch for pedestrians” sign, but this area is dark and has no shoulder - questions from general public about suitability of location. VTrans installed these signs on behalf of concerned citizens who walk along this section of road. It is unlit and shoulder widths are narrow so the signs serve as a warning to motorists to expect random pedestrian activity ahead. Sign locations are deemed appropriate by VTrans Traffic Operations. | Evaluate signage and/or road markings | No action needed | VTrans (Traffic Operations) |  |  |  |  | 40.7 | -1 | 3.52 | 0